# C12-0571-IDecision No. C12-0571-I

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

12M-165EDOCKET NO. 12M-165E

IN THE MATTER OF THE DESIGNATION OF ELECTRIC UTILITY TRANSMISSION FACILITIES AND ELECTRIC UTILITY GENERATION FACILITIES FOR WHICH AN APPLICATION TO OBTAIN A CERTIFICATE OF PUBLIC CONVENIENCE AND NECESSITY IS REQUIRED OR THE FILING OF A FORMAL DETERMINATION THAT NO CERTIFICATE IS REQUIRED.

order PROVIDING notice of
filing AND ESTABLISHING
OPPORTUNITY TO FILE COMMENTS

Mailed Date:  	  June 5, 2012

Adopted Date:  	May 30, 2012

TABLE OF CONTENTS

I.	BY THE COMMISSION	1

A.	Statement	1

II.	ORDER	24

A.	The Commission Orders That:	24

B.	ADOPTED IN COMMISSIONERS’ WEEKLY MEETING May 30, 2012.	25

## BY THE COMMISSION

### Statement

- Rule 3206(c) of the Commission’s Rules Regulating Electric Utilities, 4 Code of Colorado Regulations 723-3, requires each Colorado electric utility to file with the Commission, no later than April 30 of each year, information on its proposed new construction or extensions of transmission facilities for the next three calendar years.

- Rule 3206(d)(2)(A) provides that the Commission will give notice of the filing of data to all those who, in the opinion of the Commission, are interested persons, firms, or corporations.  Any interested person, firm, or corporation may file comments regarding the projects identified by the information filed with the Commission by June 15, 2012.

- The following utilities have filed information on proposed construction projects as listed:

INVESTOR-OWNED UTILITIES

Black Hills/Colorado Electric Utility Company, L.P.

No new projects were filed.

1.	Baculite Mesa-Overton 115 kV Line Upgrade Project

Baculite Mesa-Overton 115 kV Line Upgrade Project will rebuild the existing Baculite Mesa-Northridge 115 kV transmission line between Baculite Mesa and the future Overton substation.  The project will also upgrade equipment ratings in the Northridge 115 kV substation and the short transmission line segments into and out of the substation.  These upgrades will provide additional transmission capacity to improve reliability and facilitate the interconnection of additional generation at Baculite Mesa.  The Baculite Mesa-Overton 115 kV line is approximately four miles long.  No certificate of public convenience and necessity (CPCN) is required per Decision No. C11-0749 in Docket No. 11M-317E issued July 12, 2011.  The in-service date is 2012 with an estimated cost of $2.0 million.

2.	Reader-Rattlesnake Butte 115 kV Project

The Reader-Rattlesnake Butte 115 kV Project includes constructing a new 115 kV transmission line between the existing Reader and the new Rattlesnake Butte 115 kV substations, constructing the new Rattlesnake Butte 115 kV substation and terminal equipment additions at the Reader 115 kV substation to accommodate the new line.  These facilities will facilitate delivery of renewable energy to Black Hills/Colorado Electric Utility Company, LP (Black Hills) customer load.  This line is approximately 36 miles long.  The project also includes the rebuild of the Reader-Greenhorn 115 kV line, which was previously approved as in the ordinary course of business in Decision No. C10-0644 in Docket No. 10M-206E issued June 24, 2010.  No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is October 2012 with an estimated cost of $15.6 million.

3.	Second Boone 230/115 kV Transformer

The Second Boone 230/115 kV Transformer Project consists of adding a 150 MVA 230/115 kV transformer bank at the Boone substation.  This project will improve system reliability in the Boone and La Junta area and will enhance load serving capability in the Rocky Ford and La Junta area by providing redundant transformation at the Boone substation.  An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E. The project is estimated to cost approximately $5.3 million with an estimated in-service date of 2014.

4.	Cañon City Capacitor Bank

The Cañon City Capacitor Bank Project includes adding a 10 MVAr capacitor bank at the Cañon City 69 kV substation in 2012 and a 10 MVAr capacitor bank at the 115 kV substation in 2013.  This project will improve system reliability in the Cañon City area and in support of compliance with House Bill-1365.  No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The total project cost is estimated at $0.5 million with an estimated in-service date of September 2012 for the 69 kV capacitor, and December 2013 for the 115 kV capacitor.

5.	Portland-West Station #2 115 kV Transmission Line and Associated Substation Expansion Project

The Portland-West Station #2 115 kV Transmission Line and Associated Substation Expansion Project will improve reliability in the Cañon City area and was identified in BHCE’s 2009 Senate Bill (SB)-100 report.  The line is approximately 20 miles long.  The in-service date is December 2012 with an estimated cost of $12.5 million. No CPCN is required per Decision No. C11-0363, Docket No. 11A-157E issued April 6, 2011.

6.	Pueblo-Hyde Park-West Station 115 kV Transmission Line Rebuild Project

The Pueblo-Hyde Park-West Station 115 kV Transmission Line Rebuild Project will increase the line rating for improved reliability in the Pueblo area and was identified in BHCE’s 2009 SB-100 report.  The line is approximately 4.5 miles long.  The in-service date is 2013 with an estimated cost of $2.7 million. No CPCN is required per Decision 
No. C10-0644, Docket No. 10M-206E.

7.	Reader 115/69 kV Transformer Replacement Project

The Reader 115/69 kV Transformer Replacement Project will improve reliability in the Pueblo area and provide additional transformation capacity.  The existing 41 MVA units will be replaced with 80 MVA units.  The in-service date is 2013 with an estimated cost of $6.5 million. No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

8.	La Junta-Tri-State Interconnect

Add additional transformation capacity at the Black Hills La Junta substation and add a new half-mile 115 kV line between the Black Hills La Junta substation and the Tri-State Generation and Transmission Association, Inc. (Tri-State) La Junta substation.  This project will provide for enhanced reliability to both the Black Hills and Tri-State 115 kV systems in the La Junta area.  The in-service date is 2014 with an estimated cost of $6.0 Million.  No CPCN required per Decision No. C09-1240, Docket No. 09M-392E issued October 30, 2009.

9.	Overton 115 kV Substation

Construct a 115 – 13.8 kV substation to provide additional voltage support and capacity for load growth in the Pueblo area.  The in-service date is 2013 with an estimated cost of $5.5 million. No CPCN is required per Decision No. C07-0553, Case No. 6396 issued June 29, 2007.

Public Service Company of Colorado (PSCo)

1.	Pawnee – Daniels Park 345 kV Transmission Line Project -new project.

This project consists of building approximately 125 miles of new 345 kV transmission circuit between the Pawnee Substation and the Daniels Park Substation.  The transmission circuit will likely interconnect with the Missile Site Substation and the proposed Harvest Mile Substation.  The proposed Harvest Mile Substation Project has been contained in prior 3206 Reports.  The status of the Harvest Mile Substation Project is described in the 3206 Report in the section entitled “Status of Projects Contained in Prior Reports” at Item # 47, infra.  This project has been identified in Public Service Company of Colorado’s (Public Service or the Company) prior SB 07-100 filings, and was also mentioned in the proceedings to obtain a CPCN for the Pawnee – Smoky Hill 345 kV Transmission Project.  The Pawnee – Daniels Park 345 kV Transmission Line Project will accommodate additional generation resources in northeast Colorado.  The region has been designated in the Company’s prior 
SB 07-100 filings as Energy Resource Zone 1 (ERZ-1).  ERZ-1 has a high potential for wind generation development.  In addition, Public Service Resource Planning personnel believe the region has good potential for 
gas-fired generation development.  This project also improves reliability of the Public Service transmission network by completing a 345 kV path along the Front Range from Pawnee Substation to the Comanche plant in Pueblo.  This new 345 kV transmission line will be located in Morgan, Adams, Arapahoe, and Douglas Counties, between the existing Pawnee and Daniels Park Substations.  The in-service date is 2012-19 with an estimated cost of $147 million.

2.	Weld – DCP Midstream 115 kV Line-new project.

In this project the Company proposes to construct a new 115 kV transmission line; approximately nine miles in length, from the Weld Substation to the DCP Midstream Substation (located approximately three miles west of the town of Lucerne).  This transmission line will be a single 115 kV circuit routed along the northwestern area of Greeley and will require an expansion of existing transmission corridor or acquisition of new transmission corridor.  With the completion of the “Monfort – DCP Midstream 115 kV Line” described below and in the Company’s Petition for Declaratory Order filed on March 9, 2012 in Docket 
No. 12D-227E, constructing this proposed transmission circuit from Weld Substation to DCP Midstream Substation will provide an alternative 115 kV transmission source from Weld Substation to Monfort Substation (Weld – DCP Midstream – Monfort).  The project will increase the reliability of the 115 kV system in Greeley, as well as increase reliability to the DCP Midstream Substation. This project eliminates thermal overloads on the Weld - Arrowhead Lake 115 kV line under certain single contingency outage conditions. This project also provides added capacity on the 115 kV system for future load growth in the area. The proposed 115 kV line will be built from the Weld Substation to the DCP Midstream Substation, both located in Weld County, Colorado.  The in-service date is 2015 with an estimated cost of $15 million.

3.	Monfort to DCP Midstream 115 kV Line-new project.

A Petition for Declaratory Order was filed on March 9, 2012 seeking a declaration from the Commission that the construction of a single circuit, 3.5-mile, 115 kV radial transmission line to provide interconnection between DCP Midstream LP’s Plant No. 9 and Public Service’s Monfort substation is in the ordinary course of business and does not require a CPCN from the Commission.  The estimated cost of the project is $10,650,000.  The Commission decided in Decision No. C12-0306, Docket No. 12D-227E issued March 22, 2012, that no CPCN is required.

4.	Rifle (Ute) 138/69 kV, 75 MVA Transformer (Replacement)-new project.

This project consists of replacing the 138/69 kV, 25 MVA transformer at the Rifle (Ute) Substation with a 138/69 kV, 45/60/75 MVA transformer. The project is needed to alleviate thermal overloads on the existing Rifle (Ute) 138/69 kV, 25 MVA transformer under certain single contingency outage conditions.

In August 2008, the Commission approved Public Service’s plan to shut down the Cameo Generation Station. The 73 MW Cameo coal-fired generating plant was located in the De Beque Canyon of the Colorado River, east of Grand Junction. In late 2009, Public Service Transmission Planning personnel conducted an independent study entitled the “Cameo Generation Retirement and Replacement Study.” The study concluded that there was a need to install a second 138/69 kV, 25 MVA transformer and to replace the existing 25 MVA transformer with a larger transformer.  Based on cost estimates, the least cost alternative of replacing the existing transformer with a 138/69 kV, 45/60/75 MVA transformer was selected.  The new transformer will be located inside the existing Rifle (Ute) Substation in Garfield County, Colorado.

Planning for this project began in August 2009.  Construction of this project was planned to start in February 2011. The original planned 
in-service date for this project was May 2011.

Construction of this project hinged on meeting operational requirements that were to be provided by completing 230 kV and 69 kV projects at both the Cameo Decommissioning and the Hopkins 230-115 kV Transformer Projects.  Because both of those projects were delayed, progress on the Rifle (Ute) 138/69 kV, 75 MVA Transformer (Replacement) Project was also delayed.  According to the new schedule, construction for this project will not start until September 2012. The current in-service date is February 2013.  The estimated cost is $3.72 million.

According to Public Service, when this project was conceived the Commission’s planning rules in effect at the time did not require this project to be included in the Company’s 3206 Reports.  Therefore, it was not included in the Company’s 3206 Report filed on April 30, 2010.  However, this project should have been included in the Company’s April 30, 2011 3206 Report, but failed to do so due to an administrative oversight.  The Company includes this project in this 2012 report to advise the Commission of its existence.

5.	Hopkins 230/115 kV, 100 MVA #2-new project.

In this project the Company proposes to install a second 230/115 kV, 100 MVA transformer at the existing Hopkins Substation. The project is needed to alleviate thermal overloads on the Hopkins 230/115 kV, 100 MVA Transformer #1 under certain single contingency outage conditions. The flow across the Hopkins 230/115 kV, 100 MVA Transformer #1 is primarily impacted by three factors - local area loads (Mountain Area), Shoshone Hydro generation levels, and TOT 5 Transfer Path flows. During winter peak demand conditions and higher west-to-east TOT 5 flows, the Hopkins 230/115 kV Transformer #1 overloads beyond 100 percent of its thermal rating for single contingency loss of Hayden - Foidel Creek 230 kV or the Foidel Creek - Wolcott 230 kV or the Hopkins - Malta 230 kV lines. The second 230/115 kV, 100 MVA #2 transformer will alleviate single contingency thermal overloads on the Hopkins 230/115 kV, 100 MVA #1 transformer. The second transformer will be located inside the existing Hopkins Substation in Garfield County, Colorado.

This project is currently under construction and scheduled to be in-service in June 2012. The planning and budgeting process for the Hopkins 230/115 kV, 100 MVA #2 project began in January 2009.  Pursuant to the Commission’s transmission planning rules in place on April 30, 2009 when Public Service filed its Rule 3206 Report, this project was classified as being in the ordinary course of business, and was not required to be included in the Rule 3206 Report.  Construction on the Hopkins Project began on November 15, 2010.  However, the project experienced significant delays due to weather, and operational limitations caused by delays in the Cameo Station decommissioning and emergent line up-rate projects.  The project currently has an in-service date of June 1, 2012, with an estimated cost of $8.4 million.

According to Public Service, when this project was conceived the Commission’s planning rules in effect at the time did not require this project to be included in the Company’s 3206 Reports.  Therefore, it was not included in the Company’s 3206 Report filed on April 30, 2010.  However, this project should have been included in the Company’s April 30, 2011 3206 Report, but failed to do so due to an administrative oversight.  The Company includes this project in this 2012 report to advise the Commission of its existence.

6.	Hayden 230/138 kV, 250 MVA #KZ2A Transformer (Replacement, Western Area Power Administration’s Project)-new project.

This project would replace the existing 230/138 kV, 150 MVA #KZ2A transformer at the Western Area Power Administration’s (Western) Hayden Substation with a 230/138 kV, 250 MVA transformer. The project is 100 percent owned and operated by Western.  Public Service will have capacity rights in this transformer.  Public Service requires this capacity in order to continue supplying station service power to its Hayden generation plant and Yampa Valley Rural Electric Association loads at Mt. Harris Substation, both of which are currently being served by Hayden transformers through a transmission service contract. Western is proposing this transformer replacement project in order to eliminate thermal overloads on the existing 230/138 kV, 150 MVA#KZ2A transformer when the other parallel 230/138 kV, 250 MVA #KZ1A transformer is not available. Western has also described this project in their Rule 3627 Report on page D-10.  The agreement between Western and Public Service 
(SLC-0229 Exhibit F) stipulates that parties negotiate good faith participation in the projects when the transformer needs to be replaced.  Pursuant to the discussions between the participating entities (Western, 
Tri-State,  and Public Service), Western will be responsible for installing and maintaining the transformers and Public Service will have 20 percent capacity rights in the transformer.  This project will be located inside Western’s Hayden Substation in Moffat County, Colorado.  
The in-service date is 2014, with an estimated cost of $2.02 million (Public Service’s share, transmission dollars).

7.	Leetsdale 230/115 kV, 280MVA #2-new project.

In compliance with the final Commission Order in the Clean Air Clean Jobs Act (CACJA) in Docket No: 10M-245E, Public Service will retire Cherokee Units 1 & 2 in 2012.  Public Service also plans to operate Arapahoe Unit 4 only as needed during peak system conditions.

As was foreshadowed in the Settlement Agreement approved by the Commission in Docket No. 11A-209E, in the Company’s view it is likely that the Arapahoe 3 synchronous condenser approved in the CACJA docket will not be needed, and that the unit can be retired.  See Decision 
No. R11-0854, Docket No. 11A-209E issued August 5, 2011.  Finally, Public Service’s contracts for power from Arapahoe Units 5, 6, and 7 and Valmont Units 7 and 8 expire in 2012. Under these conditions, the Capitol Hill – Denver Terminal 115 kV underground line (L9007) can become overloaded during 2014 summer peak load conditions under certain generation dispatch patterns after the forced outage (contingency) of the Leetsdale 230/115 kV#1 auto-transformer. With Cherokee Unit 4 unavailable due to its unscheduled (forced) outage, this contingency causes the Capitol Hill – Denver Terminal 115 kV underground line # L9007 to overload to 119 percent of its 131 MVA summer normal rating.

To mitigate this potential overload, the preferred solution is to add a second Leetsdale 230/115 kV auto-transformer to effectively eliminate the contingency causing the overload. The next best alternative would be to upgrade the Capitol Hill – Denver Terminal 115 kV line with a new underground cable.  Due to the access limitations to the Capitol Hill – Denver Terminal 115 kV line for construction, this alternative is not being pursued. The Leetsdale 230/115 kV, 280 MVA #2 transformer project was recommended by the Commission as part of its CACJA order.

This project will be located inside the Leetsdale Substation in Denver, Colorado.  The in-service date is May, 2014, with an estimated cost of $8.69 million.

8.	Glenn 230/13.8 kV, 50 MVA#3-new project.

The transmission portion of this project consists of installing the 230 kV substation transmission facilities required to supply a third 230/13.8 kV, 50 MVA distribution transformer and associated equipment at the existing Glenn Substation. The third transformer is needed to provide reliability to the distribution loads and avoid thermal overloads on the two existing transformers during a single contingency outage of the other transformer. This project will be located inside the existing Glenn Substation in Adams County, Colorado.  The in-service date is November, 2015, with an estimated cost of $0.18 million.

9.	40 MVar Reactors at Midway and Waterton Substations-new project.

In this project the Company proposes to install one 13.8 kV, 40 MVar reactor on the tertiary winding of each of the 345/230/13.8 kV, 560 MVA transformers at Midway and Waterton Substations. The reactors are required to compensate for the capacitive line charging Vars (Volt Ampere Reactive) produced by the Midway - Waterton 345 kV line which results in high voltages at the Midway 345 kV and Waterton 345 kV buses. The high voltages are aggravated during light load conditions or when Comanche unit #3 is offline. In addition, the Comanche-Daniels Park 345 kV lines #1 and 2 are also producing capacitive line charging Vars which further increase the high voltages. The need for this project exists at present and the current operational practice is to take one of these 345 kV lines out of service under high voltage conditions. Taking lines out of service is not a preferred alternative as it affects the reliability of the system.  Installation of the 40 MVar reactors at the Midway and Waterton transformers will help maintain voltage at the buses below 1.05 per unit, and will provide operational flexibility. The Midway Substation is located in El Paso County, Colorado and Waterton Substation is located in Douglas County, Colorado. The in-service date is October, 2014, at a cost of $3.48 million.

10.	Mt. Harris 138/69 kV, 50 MVA #2-new project.

This project consists of adding a second Mt. Harris 138/69 kV, 50 MVA transformer at Public Service’s Mt. Harris Substation. The project is needed to alleviate contingency overloads of the existing 138/69 kV, 50 MVA transformer at Mt. Harris Substation.

The Yampa Valley Electric Association (YVEA) system consists of 69 kV transmission and 44 kV transmission that provide radial transmission service to several load-serving substations in the YVEA service territory. The YVEA system is supplied through four transmission transformers - the Mt. Harris 138/69 kV, 50 MVA transformer, the Craig Transfer 230/69 kV, 50 MVA transformer, the Steamboat 230/69 kV, 50 MVA transformer #1 and the Steamboat 230/69 kV transformer #2. YVEA can shift loads among the transformers by opening and closing transmission connections on the system. Formerly, one of the transformers could be taken out of service and the remaining three transformers could serve the YVEA system. The YVEA demand has increased to a high enough level that serving all the YVEA loads under various demand conditions with one of the transformers out-of-service is no longer possible.  System studies have shown that adding a second Mt. Harris 138/69 kV transformer will allow the Mt. Harris 138/69 kV transformer #1 or the Craig Transfer 230/69 kV transformer to be taken out-of-service and still serve the YVEA loads. The proposed project will be located inside the existing Mt. Harris Substation in Routt County, Colorado. The in-service date is May, 2014, at a cost of $6.21 million.

11.	Sheridan 115/13.8 kV, 50 MVA #2-new project.

The transmission portion of this project consists of installing the substation transmission facilities required to supply a second 115/13.8 kV, 50 MVA distribution transformer and associated equipment at Public Service’s Sheridan Substation. The second transformer is required to eliminate thermal overloads on the first existing transformer under certain single contingency outage conditions. This project will be located inside the existing Sheridan Substation in Jefferson County, Colorado. The in-service date is October, 2015, at a cost of $0.24 million.

12.	RiflePS - Parachute 230 kV Line #2

This project consists of building a second 230 kV transmission line between PSCo’s Rifle Substation and Parachute Substation. Approximately 21 miles of 230 kV transmission, rated for 576 MVA will be built using a 1-1272 kcmil conductor, in a new right-of-way. An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E. The 
in-service date is December, 2015, at a cost of $27 million.

13.	Harvest Mile 230/345 kV Substation

This project is a component of the Lamar - Front Range (LFR) Transmission Project (filed in the 2010 Rule 3206 Report). LFR studies showed that when resources are injected into the 345 kV system east of Smoky Hill Substation, the planned Smoky Hill 345/230 kV, 560 MVA auto transformers (proposed in the Pawnee - Smoky Hill 345 kV 
SB 07-100 project) have the potential to overload for single contingency outages of the other parallel transformer. Harvest Mile Substation will also accommodate future transmission projects to Spruce, Daniels, Park, and Pawnee.  An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is 2018-19, at a cost of $21 million.

14.	Plainview - Eldorado 115 kV Line Rebuild Project

Replace the existing Plainview – Eldorado 115 kV line with 115 kV transmission structures and 477 ACSR Hawk conductor rated for 150 MVA. This line has been derated to 17 MVA due to low line to ground clearance limitations of the existing “Milliken” structures, per NESC requirements. Because of the age of the existing conductor, structures, and extremely low line rating, replacement of the tower structures and conductor is required. The low rating of the present line causes system intact overloads. Line terminations and other necessary substation transmission facilities will be installed at Plainview and Eldorado Substations to accommodate the new line. The new line will be built to meet the Commission’s requirements for electromagnetic fields and noise specified in sections (e) and (f) of Rule 3206. The 115 kV line is located in Boulder and Jefferson Counties, Colorado. Per Decision No. C11-0749 in Docket No. 11M-317E, the Commission prefers to review additional information regarding the role of this project within the long-term transmission plan, and the possibility of building the project at 230 kV and initially operating it at 115 kV before making a CPCN determination.

15.	90 MVAR Capacitor Bank at Cherokee 115 kV Bus

Install a 90 MVAR capacitor bank at Cherokee 115 kV bus. This capacitor bank is needed to provide voltage support in the Cherokee area after the retirement of Cherokee #1 and #2 generating units per the Commission’s CACJA Decision Nos. C10-1328, Docket No. 10M-245E issued December 15, 2010 and C11-0121, Docket No. 10M-245E issued February 3, 2011. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The proposed project will be located inside Cherokee Substation in Adams County.  The in-service date is April 2013, at a cost of $2.28 million.

16.	Godfrey Breaker Station and 25 MVAR Capacitor Bank

Convert the existing Godfrey switching station to a Breaker station using a three-breaker ring configuration. This project is needed to provide reliability to the Greeley area after the expiration of power purchase contracts with Thermo Greeley (32 MW, 6/2011) and Thermo Power (69 MW, 8/2013). A 25 MVAR capacitor bank will be installed at Monfort 115 kV bus to provide voltage support for Eastern Greeley. The proposed project will be located inside the Godfrey Switching Station in Weld County, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is October 2013, at a cost of $4.54 million.

17.	Malta 230/115 kV, 100 MVA #2

Install a second 230/115 kV, 100 MVA transformer and associated equipment at Malta Substation. This project is required to support a 40 MW load addition at Climax Substation. Without the second transformer, the existing transformer overloads under certain single contingency outages requiring load shed. The proposed project will be located inside Malta Substation in Lake County, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is October 2013, at a cost of $13.3 million.

18.	Weld 230/115 kV, 150 MVA #3

Install a third 115/230 kV, 150 MVA transformer at Western Area Power Administration’s (WAPA) Weld Substation. This project is needed to relieve overloads on the existing 115/230 kV transformers (PSCo and WAPA transformers) at Weld Substation for single contingency outage of either transformer. This project is a joint project between PSCo and WAPA. The proposed project will be located inside WAPA’s Weld Substation in Weld County, Colorado. An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is April 2013, at a cost of $3 million.

19.	45 MVAR Capacitor Bank at Cameo 230 kV Bus

Install a 45 MVAR switched shunt capacitor bank at Cameo 230 kV bus. This project is needed for voltage support in the area because of the retirement of Cameo generation and to support future load growth in the area. The proposed project will be located inside Cameo Substation in Mesa County, Colorado. An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E. The in-service date is December 2012, at a cost of $1.07 million.

20.	45 MVAR Capacitor Bank at Parachute 230 kV Bus

Install a 45 MVAR switched shunt capacitor bank at Parachute 230 kV bus. This project is needed to support load growth in the Starkey Gulch area. The proposed project will be located inside Parachute Substation in Garfield County, Colorado. An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is December 2012, at a cost of $1.73 million.

21.	Bancroft 115/13.8 kV, 50 MVA #3.

The distribution portion of the project consists of installing a third 115/13.8 kV, 50 MVA transformer at Bancroft Substation. The transmission portion of the project consists of installing the 115 kV substation transmission facilities required to supply the new transformer and associated equipment. This project is needed to relieve overloads on the existing transformers for single contingency outage of either transformer. The proposed project will be located inside Bancroft Substation in Lakewood, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E. The in-service date is January 2013, at a cost of $0.3 million.

22.	90 MVAR Capacitor Bank at Arapahoe 115 kV Bus

Install a 90 MVAR Capacitor bank at Arapahoe 115 kV bus. This project is needed to provide voltage support in the Arapahoe area after the retirement of Arapahoe #3 generating unit per the Commission’s CACJA Decision Nos. C10-1328 and C11-0121. The proposed project will be located inside Arapahoe Substation in Denver, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is December 2013, at a cost of $3.34 million.

23.	Federal Heights 115/13.8 kV, 50 MVA #3

The distribution portion of the project consists of installing a third 115/13.8 kV, 50 MVA transformer at Federal Heights Substation. The transmission portion of the project consists of installing the 115 kV substation transmission facilities required to supply the new transformer and associated equipment. This project is needed to avoid overloading of the existing transformers under a single contingency outage of either transformer. The proposed project will be located inside Federal Heights Substation in Federal Heights, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is March 2013, at a cost of $0.25 million.

24.	Havana 115/13.8 kV, 50 MVA #3

The distribution portion of the project consists of installing a third 115/13.8 kV, 50 MVA transformer at Havana Substation. The transmission portion of the project consists of installing the 115 kV substation transmission facilities required to supply the new transformer and associated equipment. This project is needed to avoid overloading of the existing transformers in case of a single contingency outage of either transformer. The proposed project will be located inside Havana Substation in Denver, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is June 2013, at a cost of $0.41 million.

25.	Jewell 230/13.8 kV, 50 MVA #3

The distribution portion of the project consists of installing a third 230/13.8 kV, 50 MVA transformer at Jewell Substation. The transmission portion of the project consists of installing the 230 kV substation transmission facilities required to supply the new transformer and associated equipment. This project is needed due to the lack of distribution tie back up support in case of a single contingency outage of one of the existing transformers. The proposed project will be located inside Jewell Substation in Arapahoe County, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is February 2013, at a cost of $0.1 million.

26.	Chambers 230/115 kV, 280 MVA #2

Install a second 230/115 kV, 280 MVA transformer at Chambers Substation. This project is needed to avoid overloading of the existing transformer under certain double-contingency outages and for increased reliability. The proposed project will be located inside Chambers Substation in Aurora, Colorado. An application for a CPCN or an application for a formal determination that no CPCN is required shall be filed per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is June 2013, at a cost of $5.2 million.

27.	Lacombe 230/13.8 kV, 50 MVA #3

The distribution portion of the project consists of installing a third 230/13.8 kV, 50 MVA transformer at Lacombe Substation. This project is needed to provide load relief for the 2nd network under system intact conditions and to construct the 14th network off the new Lacombe #3. The transmission portion of the project consists of installing the 230 kV substation transmission facilities required to interconnect the third transformer and associated equipment. The proposed project will be located inside Lacombe Substation in Denver, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is May 2013, at a cost of $0.2 million.

28.	Capitol Hill 115/13.8 kV, 50 MVA #3

The distribution portion of the project consists of installing a third 115/13.8 kV 50 MVA transformer at Capitol Hill Substation. The transmission portion of the project consists of extending the 115 kV bus and installing the 115 kV transmission facilities required to supply the new transformer. This project is needed to eliminate overloads on the existing transformers for single contingency outage of the other transformer. The proposed project will be located inside the Capitol Hill Substation in Denver, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is May 2014, at a cost of $1.4 million.

29.	Russell 115/13.8 kV, 50 MVA #2

The distribution portion of the project consists of installing a second 115/13.8 kV, 50 MVA transformer at Russell Substation. The transmission portion of the project consists of installing the 115 kV substation transmission facilities required to supply the new transformer and associated equipment. This project is needed due to lack of distribution tie backup support in the area and to avoid single contingency overloads on the existing transformers for the loss of either transformer. The proposed project will be located inside Russell Substation in Arvada, Colorado. No CPCN is required per Decision No. C11-0749 in Docket No. 11M-317E.  The in-service date is June 2014, at a cost of $0.28 million.

30.	Parachute-Cameo 230 kV transmission line

The in-service date is 2019 to a drop in anticipated load growth.  Estimated cost is $48.5 million.  A CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

31.	Lamar-Front Range 345/500 kV and Lamar-Vilas 230/345 kV Transmission Project

Public Service has been evaluating alternatives with stakeholders, including Tri-State.  A CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

32.	Rifle (Ute)-Story Gulch 230 kV Transmission Line Project

The in-service date is undetermined due to a delay in customer load growth.  Estimated cost is $24.14 million.  A CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

33.	Barker Substation (Distribution)

The in-service date is 2020 at a cost of $16.4 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

34.	Brantner Substation (Distribution)

The in-service date is June 2014 at a cost of $1.76 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

35.	Wilson #1 Substation (Distribution)

The in-service date is May 2018 at a cost of $3.37 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

36.	University #3 Substation (Distribution)

The in-service date is December 2012 at a cost of $0.28 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

37.	Ault-Cherokee 230 kV Transmission Line Project

The in-service date has been delayed. The Ault-Cherokee 230 kV Line Project has been modified to include the Weld County Transmission Expansion Project. The Weld County Transmission Expansion Project is still in the early stages of development and is subject to a scope change. This project is intended to replace the Ault-Ft. Lupton section of the 
Ault-Cherokee 230 kV Line Project, and will go through a stakeholder study process with parties able to express participation interest during solicitations in 2012. This project will provide transmission service to Public Service’s retail customers in the Greeley area and aligns with the long term goals for increasing the transfer limit of the TOT 7 transfer path. The current in-service date is outside of the time period covered by this Rule 3206 Report, which is the 2013-2015 timeframe. Additional information concerning the status of this project will be provided as it becomes available.  A CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

38.	Bluestone Valley Substation.

“Bluestone Valley Substation” was contained in a prior Rule 3206 Report and reflected a 2014 in-service date in that report. The project scope has been modified to include a 230/69 kV transformer and 69 kV protection equipment at the Bluestone Valley Substation. The Bluestone Valley 230 kV yard will be laid out to accommodate the future Bluestone Valley – Clear Creek 230 kV double-circuit transmission line. A two-mile De Beque-Bluestone Valley 69 kV line will be constructed. 
The De Beque-Cameo 69 kV transmission line will be removed. The “Bluestone Valley Substation and De Beque-Bluestone Valley 69 KV Line” project has a tentative in-service date of 2015.  No CPCN is required per Decision C09-0681, Docket No. 09M-392E issued June 25, 2009.

39.	Glenwood Springs - Rifle 69/115 kV Conversion

This project was described in a prior 3206 Report and reflected an undetermined ISD. This project has a new tentative ISD of 201

40.	San Luis Valley-Calumet-Comanche Transmission Project.

A CPCN application was submitted May 14, 2009, Docket No 09A-325E and granted, in part, in Decision No. R10-1245 issued November 19, 2010.  Currently, an outage on the existing Poncha-San Luis Valley 230 kV line causes voltage collapse when the total San Luis Valley load is above 65 MW. There is also a potential for overloading of the Stem BeachWalsenburg 115 kV line in the event of an outage of the 
Comanche- Walsenburg 230 kV line. The Stem Beach - Walsenburg overload is addressed by a Remedial Action Scheme (RAS) that opens 
Tri-State's Walsenburg - Gladstone 230 kV line, which results in loss of Tri-State load in northeastern New Mexico. The project will increase reliability in the area while also allowing for significant new generation injection in the San Luis Valley and Walsenburg areas.

41.	Poncha Junction 115/230 kV Auto Transformer (280 MVA)

The in-service date changed from 5/2013 to 11/2013 due to construction delays in relocating Western’s lines. Western has committed to 20 percent capacity in this project. The project scope will also include 40 MVar reactors on the tertiary winding of the 230/115/13.8 kV, 280 MVA transformer. The reactors will compensate for the capacitive charging on the line, and reduce high voltages in the San Luis Valley area under system intact conditions.  The in-service date is November 2013 at a cost of $8.4 million.  No CPCN is required per Decision No. C09-0681, Docket No. 09M-392E.

42.	Gunbarrel Substation

The proposed in-service date for this project is September 2012 at a cost of $627,000.  No CPCN is required per Decision No. C08-0676, Case No. 6396 issued July 8, 2008.

43.	New Castle 115/69-24.9 kV Substation (New Castle 115-24.9 kV, 16 MVA)

The project now involves the installation of a 115-24.9 kV, 16 MVA distribution transformer.  The project has been renamed “New Castle 
115-24.9 kV, 16 MVA.”  No CPCN is required per Decision 
No. C08-0676, Case No. 6396.

44.	Missile Site 345 kV Substation

A CPCN application, Docket No. 10A-240E, was filed April 16, 2010 and was granted in Decision No. C10-0552 issued June 8, 2010.  The in-service date is January 2013 at a cost of $14 million.

45.	Pawnee-Smoky Hill 345 kV Transmission Line Project

The Commission granted PSCo a CPCN for this project on February 26, 2009, Decision No. C09-0048, Docket No. 07A-421E.  The in-service date is January 2013.

46.	Niwot - Gunbarrel Load Service Request 230 kV Underground Line Project

The in-service date is May 2012 at a cost of $9.80 million.  No CPCN is required per Decision No. C08-0676, Case No. 6396.

47.	Ptarmigan Substation

Public Service continues its siting activities for a new distribution substation.  The project involves a transmission line tap on the existing Dillon-Blue River 230 kV transmission line to a “to-be-determined” substation site, and construction of feeders from the new substation facility to interconnect with the existing distribution system in the Silverthorne area.

As described in the Company’s 2011 3206 Report, in 1999 Summit County denied Public Service’s application for approval of a substation site and transmission line tap after the Company identified a preferred site through a comprehensive siting process that included substantial public involvement.  Public Service decided to not appeal Summit County's denial, and instead built a four-mile express feeder from the Dillon Substation into the Silverthorne area to help address reliability concerns.  Over time, load growth in the area has continued to stress the delivery system driving the need for this new substation to serve existing and future customers.

Since its last 3206 Report, Public Service has been searching for a potential site.  Finding an acceptable location for this distribution substation and associated facilities continues to be very challenging due to the mountainous topography, vocal opposition to any substation site near existing subdivisions, environmental sensitivities, and the visual qualities of the area.  However, Public Service continues to actively investigate potential sites while considering a variety of the substation designs to help minimize potential impacts.

The current forecasted capital cost is $6.3 million at the transmission level and $17.1 million at the distribution level (not including feeder work). Over time, land availability, land price escalation, increased construction costs, and equipment price increases have contributed to this substantial escalation in costs.

48.	Happy Canyon 115 kV Network Interconnection with IREA – formerly reported by IREA.

The transmission project cost estimate is $1.77 million with an in-service date of December 2017.  No CPCN is required per Decision No. C06-0761, Case No. 6396 issued July 3, 2006.

RURAL ELECTRIC ASSOCIATIONS

Grand Valley Power

Grand Valley filed a letter indicating that it has no plans for new generation or transmission facilities within the next three years.

Intermountain Rural Electric Association, Inc.

1.	Shaffers Crossing to Pine Junction 115 kV Transmission Line-new project.

The cost of this project is $1.2 million with an in-service date of November 2013.

2.	Phase 1 - Conifer to Shaffers Crossing 115 kV transmission line

Construction is scheduled to begin in March 2014; complete/in-service, November 2014; at an estimated cost of $1.3 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

3.	Phase 2 - Conifer to Shaffers Crossing 115 kV transmission line

Construction is scheduled to begin in March 2015; complete/in-service, November 2015; at an estimated cost of $1.3 million.  No CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

4.	Wolfensberger-Citadel 115 kV Transmission

The cost of this project is $1.2 million with an in-service date of April 2015.  No CPCN required per Decision No. C06-0761, Case No. 6396.

5.	Citadel Substation

The cost of this project is $4.0 million with an in-service date of April 2013.  No CPCN required per Decision No. C07-0553, Case No. 6396.

6.	Como Substation

The cost of this project is $5.0 million with an in-service date of October, 2012.  No CPCN required per Decision No. C07-0553, Case No. 6396.

La Plata Electric Association, Inc.

No filing was submitted.

Mountain View Electric Association, Inc.

No filing was submitted.

San Miguel Power Association

No filing was submitted.

Tri-State Generation and Transmission Association, Inc. (Tri-State)

1.	Davis Delivery Point-new project

To serve the new Anadarko Lancaster Plant (gas compression and petroleum refining) by interconnecting with an existing 115 kV transmission line between Fort Lupton and Hudson owned by Xcel Energy (Xcel). Tri-State intends to construct a short (1.5 mile) 115 kV radial transmission line (795 ACSR conductor) from Xcel's line to serve a new substation (Davis), which is to be constructed at the Anadarko site. The new Davis substation will initially include a single 40 MVA 115-13.2 kV transformer, with provisions for additional transformation. It is to be located in United Power's service territory, in Weld County, north and east of Fort Lupton. Tri-State considers the project to be "in the ordinary course of business" since the facilities will be designed for 115 kV and the 1.5 mile transmission line will be a radial line terminating at the Anadarko premises. Both Anadarko and United Power will take distribution service from the Davis substation. All facilities associated with the Davis Delivery Point project are load-serving facilities and do not materially affect 
Tri-State's ten-year Plan as presented in its PUC 3627 filing.  The 
in-service date of this project is 2013, with an estimated cost to be determined.

2.	DCP Midstream 115 kV Delivery Point-new project

To serve the new LaSalle Natural Gas Processing Plant (to be owned and operated by DCP Midstream) by interconnecting with an existing 115 kV transmission line (Weld-Kiowa Creek) owned by the Western Area Power Administration, and constructing a short (two-mile) radial transmission line (795 ACSR conductor, single steel pole) to serve a new substation (South Kersey), which is to be constructed adjacent to the gas plant. The new South Kersey substation will include a 115 kV breaker, 20 MVA 
115-4.16 kV transformer, and 4.16 kV metering. It is to be located in Poudre Valley Rural Electric Association's (PVREA) service territory, in Weld County, about two miles southwest of the Town of Kersey. This project was submitted in Tri-State's PUC 3627 filing. Tri-State considers the project to be "in the ordinary course of business" since the facilities will be designed for 115 kV and the transmission line will be a radial line serving a single customer and terminating at the customer's premises.  The in-service date of this project is 2013, with a cost of $0 to Tri-State.

3.	Olive Creek 115 kV Delivery Point (Formerly Williams-Midstream Wray Project

To serve a gas pipeline pumping station located south and east of Wray, Colorado and operated by Williams-Midstream. The liquid natural gas pumping load will be approximately 5 MW. The proposed project will provide adequate transmission system capacity, voltage support, and reliability to the customer.

The project was submitted in Tri-State's 3627 filing with a change in project scope from the 3206 supplemental filing. Instead of a radial line extending from the Wray Substation, as was originally envisioned, the project will now interconnect (at Olive Creek Tap) to Tri-State's existing WrayVernon Tap 115 kV transmission line south of the Wray Substation. A new radial 115 kV transmission line will be constructed from that interconnection approximately three miles to the Williams-Midstream Wray facility. Tri-State will add 115 kV breakers at Vernon Tap.

Consistent with the original project scope, Tri-State considers the revised project scope to also be "in the ordinary course of business" since the facilities will be designed for 115 kV and since the transmission line extension will be a radial line serving a single customer terminating at the customer's premises.

This project was submitted to the CPUC on May 13, 2011 as a supplement to Tri-State's 2011 3206 filing.  CPCN Decision No. C11-0749 determined that no CPCN is required. The estimated cost of the project to Tri-State is $0.  The in-service date is 2013.

4.	Gunbarrel 230 kV DP

Construction of a new delivery point at Xcel's existing 230 kV Gunbarrel Sub for service to PVREA. Tri-State is proposing to install a 25 MVA 23024.9 kV power transformer to be served from an expansion of Xcel's 230 kV bus in conjunction with Xcel's plan to construct another 230 kV line termination at the substation for service to IBM. The project will allow Poudre Valley to maintain adequate system reliability to the existing and projected loads to the north and west of the Gunbarrel Substation, outside of the City of Longmont, that are currently served from long distribution feeders from the Hygiene and Dow Flats substations. Load is expected to be transferred from Hygiene and Dow Flats to this new delivery point.  The in-service date is 2012.  A CPCN is not required pursuant to Decision No. C11-0749.  The estimated cost of the project is $3.092 million.

5.	Carey 230 kV Substation

Construction of a new tap and substation sectionalizing PRPA's 
Ault-Timberline 230 kV transmission line for delivery to PVREA. This new distribution substation will enable Poudre Valley to serve existing load and new load in the vicinity of Severance, Windsor, and Timnath caused by the growth of these communities along the interstate corridor. The proposed project will provide transmission system capacity, voltage support, and reliability to Poudre Valley's existing customer load that currently must be served from a combination of five other distribution substations (Black Hollow, Boxelder, Airport, Trilby, and Windsor.)  A CPCN is not required per Decision No. C11-1126 in Docket 
No. 11A-735R issued October 25, 2011.  The in-service date is 2013 at a cost of $6.807 million.

6.	Burlington-Wray 230 kV Line

The in-service date is 4Q 2015 at a cost of $40.27 million.  A CPCN was required pursuant to Decision No. C10-0644, Docket No. 10M-206E, and was granted in Decision No. C11-0042, Docket No. 10A-906E issued January 14, 2011.

7.	La Junta 69 kV Tie Line Addition

The in-service date is 2014 at a Tri-State cost of $0.578 million.  A CPCN is not required pursuant to Decision No. C10-0644, Docket 
No. 10M-206E.

8.	Lamar-Front Range and Lamar-Vilas Transmission Project

The Lamar to Front Range project is in the development stage. Tri-State has been evaluating technical studies for several alternatives in cooperation with a variety of stakeholders. The current in-service date is outside the time period required for the Rule 3206 filing. Additional information concerning the status of this project will be provided as it becomes available. The Lamar-Vilas transmission project is also in the planning stage. Tri-State has been evaluating technical studies for several alternatives in cooperation with a variety of stakeholders. The current 
in-service date is outside the time period required for the Rule 3206 filing. Additional information concerning the status of this project will be provided as it becomes available.  A CPCN is required per Decision No. C10-0644, Docket No. 10M-206E.

9.	Bayfield 115/69 kV Transformer Replace

The Tri-State estimated cost is $.65 million with an in-service date of 2014.  No CPCN is required per Decision No. C09-0681, Docket No. 09M-392E.

10.	Bullock #2 115/69 kV Transformer Replace.

Tri-State’s cost of the project is $1.1 million with an in-service date of 2013. No CPCN is required per Decision No. C09-0681, Docket 
No. 09M-392E.

11.	LPEA-San Juan Project

Tri-State’s share of the project cost is $129.5 million with an in-service date of 2015.  CPCN required per decision No. C09-0681, Docket No. 09M-392E.

12.	Big Sandy-Lincoln-Midway 230 kV Line

The in-service date is 2013 at a cost of $15.5 million.  No CPCN required per Decision No. C08-0676, Case No. 6396.

13.	Deering Lake-Wray (T-S) 115 kV Reliability Additions

The in-service date is 2012 at a cost of $3.6 million.  No CPCN required per Decision No. C05-0826, Case No. 6396 issued July 1, 2005.

14.	Nucla-Telluride 115 kV Transmission Line

Tri-State’s cost of the project is $55.9 million with an in-service date of 2012.  A CPCN was granted per Decision No. C01-1059, Docket No. 01A-252E issued October 18, 2001.

15.	Delta County 115 kV Transmission Line Improvement (formerly Garnet Mesa 115 kV Loop Service)

Tri State’s share of this project is $10.2 million.  The in-service date is 2014.  No CPCN is required per Decision No. C03-0707, Case No. 6396 issued June 27, 2003.

16.	East Montrose 115 kV Delivery Point

The cost is $12.4 million with an in-service date of 2013.  No CPCN is required per Decision No. C06-0761, Case No. 6396.

17.	FARR-Windy Gap 138/69 kV Double Circuit Loop Project

This project’s cost is $14.3 million and has an in-service date of 2013.  No CPCN is required per Decision No. C90-1125, Case No. 6396 issued August 22, 1990.

18.	Plaza-Waverly 115 kV Loop Project

Tri-State’s cost is $10.9 million.  This project has an in-service date of 2013.  No CPCN required per Decision No. C07-0553, Case No. 6396.

19.	United Power System Improvement Project – Phase III

The in-service date is 2013 at a cost to Tri-State of $4.8 million.  No CPCN is required per Decision No. C04-0725, Case No. 6396 issued July 1, 2004

20	San Luis Valley-Calumet-Comanche Transmission Project

The project will solve a critical need to improve the electric service to 
Tri-State member San Luis Valley Rural Electric Cooperative. Currently, an outage on the existing Poncha-San Luis Valley 230 kV line causes voltage collapse when the total San Luis Valley load is above 65 MW. There is also a potential for overloading of the Stem BeachWalsenburg 115 kV line in the event of an outage of the Comanche-Walsenburg 230 kV line. The Stem Beach - Walsenburg overload is addressed by a RAS that opens Tri-State's Walsenburg - Gladstone 230 kV line, which results in a loss of Tri-State load in northeastern New Mexico. The project will increase reliability in the area while also allowing for significant new generation injection in the San Luis Valley and Walsenburg areas.

Xcel has indicated that it may withdraw from participating in this project depending upon the Commission's Phase I decision in connection with Xcel's 2011 Electric Resource Plan (Docket No. 11A-869E). Xcel has indicated that it anticipates the Commission's Phase I decision sometime in the Fall of 2012 and a decision on its continued participation in the project within 30 days thereafter.  The Commission granted the CPCN in initial Decision Nos. C11-0288 issued March 23, 2011 and C11-0947 issued September13, 2011 in Docket No. 09A-325E. Estimated cost to Tri-State is $82.266 million.

21	Burdett 115 kV Delivery Point Project (Formerly Williams-Midstream Burdett Project)

Construction of a new radial 115 kV line (approximately 11 miles) from Tri-State's existing North Yuma Substation to a new 115/12.5 kV 10/14 MVA distribution substation for delivery to Highline Electric Association (Highline). The new distribution substation will enable Highline to serve a gas pipeline pumping station located near Burdett, Colorado and operated by Williams-Midstream. The liquid natural gas pumping station will consist of two 3000hp motors and ancillary loads. The proposed project will provide adequate transmission system capacity, voltage support, and reliability to the customer.  A CPCN is not required pursuant to Decision No. C11-1248, Docket No. 11M-317E issued November 22, 2011. Estimated cost to Tri-State is $0 million.

White River Electric Association, Inc.

No filing was submitted.

## ORDER

### The Commission Orders That:

- Notice is hereby given that the above investor-owned utilities and rural electric cooperative associations have submitted information concerning the proposed construction of transmission and generation facilities in accordance with Rule 3206 of the Rules Regulating Electric Utilities, 4 Code of Colorado Regulations 723-3.  Pursuant to that rule, you are notified that the information is available for inspection at the offices of the Commission during regular business hours.

- By June 15, 2012, any interested person, firm, or corporation may file comments about the projects identified by the information now filed with the Commission.  The Commission will consider any comments in determining which projects do not require a certificate of public convenience and necessity, which projects will require the utility to file an application for a certificate of public convenience and necessity, or which projects will require the utility to file for a formal determination that a certificate is not required.

- This Order is effective upon its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
May 30, 2012.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JOSHUA B. EPEL ________________________________ JAMES K. TARPEY ________________________________ Commissioners COMMISSIONER MATT BAKER RESIGNED EFFECTIVE MAY 11, 2012. |
| --- | --- |