# C18-0253-IDecision No. C18-0253-I

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING16A-0396E NO. 16A-0396E

IN THE MATTER OF THE APPLICATION OF PUBLIC SERVICE COMPANY OF COLORADO FOR APPROVAL OF ITS 2016 ELECTRIC RESOURCE PLAN.

INTERIM decision granting unopposed 
motion for Extension of Time to 
File 120-Day Report and associated 
filing dates, granting certain 
rule waivers, AND waiving RESPONSE TIME

Mailed Date:  	April 13, 2018

Adopted Date:  	April 11, 2018

TABLE OF CONTENTS

I.	BY THE COMMISSION	1

A.	Statement	1

B.	Background, Discussion	2

C.	Procedural Schedule	3

D.	Rule Waivers	3

E.	Response Time	4

II.	ORDER	4

A.	It Is Ordered That:	4

B.	ADOPTED IN COMMISSIONERS’ WEEKLY MEETING April 11, 2018.	5

## BY THE COMMISSION

### Statement

On April 10, 2018, Public Service Company of Colorado (Public Service 
or Company) filed an unopposed Motion for Partial Waiver of Rules 3613(D)-(H) to Provide 
an Extension of Time to File its 120-Day Report (Motion).  This Motion proposes to extend 
the due date to file the 120-day report by 10 days, and extend the subsequent Phase II due 
dates by approximately 10 days, to May 7, 2018.  Public Service states that the additional 
time is necessary for it to fully comply with additional portfolio requirements in Decision 
No. C18-0191, which granted the Company's request to present the Colorado Energy Plan Portfolio in the 120-day report.  The Motion also requests certain rule waivers to accommodate these extensions.

Through this Decision, we waive response time and grant the Motion.

### Background, Discussion

We issued the Phase I decision, Decision No. C17-0316, in this proceeding on April 28, 2017.  The Phase I Decision approved, with modifications, the Company’s competitive bidding proposal and plan to acquire resources to meet its anticipated resource need during an eight-year resource acquisition period from 2016 through 2023. The Phase I Decision also approved the process for evaluating bids received in the competitive solicitation and established the modeling requirements for the presentation of portfolios in Phase II.

On August 29, 2017, Public Service filed a Joint Motion to Approve a Stipulation to allow the Company to present its Colorado Energy Plan Portfolio (CEPP) for Commission consideration in Phase II of this proceeding, in addition to the portfolios required in the Phase I Decision. On October 11, 2017, Decision No. C17-0823-I established a procedural schedule for Phase II of this proceeding to accommodate the CEPP proposal.

In Decision No. C18-0191, the Commission granted the Company’s request to present its CEPP in Phase II. The Commission ordered the Company to develop a number of additional resource portfolios associated with the CEPP in its Phase II 120-Day Report to assist in the evaluation of the CEPP.

### Procedural Schedule

The Company states that it is working to develop these additional resource portfolios required by the Commission, but due to the complex and time-intensive nature of developing these models, the Company requests an extension of ten days until May 7, 2018 to file its 120-Day Report.

Public Service’s proposed modifications to the procedural schedule are as follows:

| Activity | Current Date | Proposed Date |
| --- | --- | --- |
| 120-Day Report | April 27, 2018 | May 7, 2018 |
| Independent Evaluator Report | May 29, 2018 | June 6, 2018 |
| Intervenor Comments | June 11, 2018 | June 21, 2018 |
| Company Reply Comments | June 26, 2018 | July 6, 2018 |
| Commission Decision on Phase II | July 26, 2018 | August 6, 2018 |

We find that a 10-day extension to file the 120-day report until May 7, 2018 is reasonable, in conjunction with the extension of the other Phase II dates as proposed in the Motion.  We therefore grant the extensions as proposed.

### Rule Waivers

Rule 3613(d) of the Commission’s Rules Regulating Electric Utilities, 4 Code 
of Colorado Regulations 723-3, requires that within 120 days of the utility’s receipt of bids 
in its competitive acquisition process, the utility shall file a report with the Commission, which 
is known as the 120-Day Report. Rule 3613(e) requires that within 30 days after the utility files its 120-Day Report, the Independent Evaluator (IE) selected in the proceeding shall separately file a report containing its analysis of whether the utility conducted a fair bid solicitation. Rules 3613(f) and 3613(g) provide that parties to the proceeding may file comments on the 
120-Day Report and the IE report 45 days after the 120-Day Report is filed, and that the utility may file comments to the IE report and responses to the parties’ comments within 60 days after the filing of the 120-day report. Rule 3613(h) provides that the Commission shall issue a written decision approving, conditioning, modifying, or rejecting the utility’s preferred resource plan within 90 days of the filing of the 120-Day Report.

The Company seeks partial waivers of Rules 3613(d)-(h) to allow the extension of time as proposed in the Motion.  We agree that a partial rule waiver is appropriate, and grant Public Service’s request for partial waivers of Rules 3613(d)-(h).

### Response Time

Public Service states that it contacted counsel for all parties to this proceeding regarding the Motion, and no party indicated opposition to the Motion.  We find that it is appropriate to waive response time.

## ORDER

### It Is Ordered That:

The Motion for Partial Waiver of Rules 3613(D)-(H) to Provide an Extension of Time to File its 120-Day Report (Motion), filed on April 10, 2018 by Public Service Company of Colorado (Public Service) is granted, consistent with the above discussion.  Response time is waived.

The 120-Day Report shall be filed no later than May 7, 2018.

The Independent Evaluator report shall be filed no later than June 6, 2018.

Intervenor comments are due no later than June 21, 2018.

Reply comments are due no later than July 6, 2018.

Public Service’s request for partial waivers of Rules 3613(d)-(h), 4 Code of Colorado Regulations 723-3 is granted, consistent with the above discussion.

This Decision is effective upon its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
April 11, 2018.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ FRANCES A. KONCILJA ________________________________ WENDY M. MOSER ________________________________ Commissioners |
| --- | --- |

# Footnotes

Decision No. C18-0191 was issued in this proceeding on March 22, 2018.

The Commission approves requested filing dates and understands the request to revise a requested decision date from July 26, 2018, to August 6, 2018.

The Company did not receive a stated position from Ski Resorts and the Rocky Mountain Environmental Labor Coalition and the Colorado Building and Construction Trades Council by the time it filed the Motion.