# C18-0742-IDecision No. C18-0742-I

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING15A-0589E NO. 15A-0589E

IN THE MATTER OF THE APPLICATION OF THE CITY OF BOULDER, COLORADO FOR APPROVAL OF THE PROPOSED TRANSFER OF ASSETS FROM PUBLIC SERVICE COMPANY OF COLORADO TO THE CITY AND ASSOCIATED AUTHORIZATIONS AND RELIEF.

Interim decision granting, with modifications, requests for additional 
time to satisfy commission conditions

Mailed Date:  	August 31, 2018

Adopted Date:  	August 29, 2018

TABLE OF CONTENTS

I.	BY THE COMMISSION	1

A.	Statement	1

B.	Background	2

C.	Joint Motion for Extension of Time to File a Cost Agreement and Permanent Easement Agreement and Joint Motion for Additional Time to File a Corrected List of Assets	5

D.	Findings and Conclusions	5

II.	ORDER	7

A.	It Is Ordered That:	7

B.	ADOPTED IN COMMISSIONERS’ WEEKLY MEETING August 29, 2018.	8

## BY THE COMMISSION

### Statement

By this Decision, we grant, with modifications, the Joint Request of the City of Boulder and Public Service Company of Colorado for Extension of Time to File a Cost Agreement and Permanent Easement Agreement and Joint Motion for Extension of Time to File Corrected List of Assets filed on August 24, 2018.  We grant an extension from August 24, 2018 to October 26, 2018 to file an agreement(s) regarding permanent easements for Public Service Company of Colorado (Public Service) to serve its customers in Boulder after separation of the Public Service and the City of Boulder’s (Boulder) electric distribution systems, agreement(s) regarding payment to Public Service for costs incurred to effectuate the separation of the electric distribution systems.  We also grant the request to file the corrected list of assets on October 24, 2018.  All filings shall be made at one time, as required in Decision No. C17-0750, which was issued on September 14, 2017.

### Background

By Decision No. C17-0750, issued September 14, 2017, the Commission granted, in part and with conditions, and denied, in part, Boulder’s Third Supplemental Verified Application for Approval of the Proposed Transfer of Assets from Public Service Company of Colorado.  Notably, the decision satisfied the requirements stemming from the Boulder District Court in Order Re: Judicial Review of the Colorado Public Utilities Commission Decision, City of Boulder v. Pub. Utils. Comm’n, Case No. 14CV30047 (Boulder Dist. Ct., January 14, 2015) by determining—to the extent necessary as of the date of the order—how Public Service’s facilities should be assigned, divided, or jointly used to protect Public Service’s electric distribution system’s effectiveness, reliability, and safety.

Decision No. C17-0750 directed Public Service to assist Boulder in good faith in its efforts to satisfy the conditions set forth in the decision for securing final Commission approval of the designation of assets for transfer outside of the substations.

Decision No. C17-0750 approved the designation of certain assets for transfer from Public Service to Boulder, subject to Boulder demonstrating compliance with three conditions.  In order to secure final approval of the designation of these assets for transfer, the Commission directed Boulder to take the following actions: (1) file an agreement reached between Boulder and Public Service that provides Public Service permanent non-exclusive easements and other necessary real property rights for the location of its electric facilities within Boulder’s city limits that are necessary for Public Service to provide service to its customers after separation; (2) correct the errors and omissions from the list of assets for transfer outside of the substations and resubmit the revised list of assets for final approval; and (3) file an agreement (or multiple agreements) between Boulder and Public Service that address(es) the payment by Boulder to Public Service of the costs incurred by Public Service to effectuate municipalization and the separation of Public Service’s system into two separate systems.  Paragraph 162 of Decision No. C17-0750 states:

Boulder shall submit no later than 90 days following the issuance of this Decision, the filings required above for final approval of the designation of assets for transfer outside the substations. Boulder shall make a single filing satisfying all requirements of the three conditions.  Boulder may file a request for additional time for good cause shown.

(Emphasis Omitted)

- On December 13, 2017, Boulder filed a Report to the Commission Regarding Agreements with Public Service Company of Colorado and Request for Additional Time to Satisfy Commission Conditions (First Request for Additional Time).  The Commission granted the First Request for Additional Time on December 22, 2017 by Decision No. C17-1065-I, extending the filing date to March 13, 2018.

- On March 13, 2018, Boulder and Public Service (Parties) filed a Joint Report to the Commission Regarding Agreements Between the City of Boulder and Public Service Company of Colorado and Request for Additional Time to Satisfy Commission Conditions (Second Request for Additional Time).  By Decision No. C18-0181-I, issued March 14, 2018, the Commission approved a second extension to June 11, 2018 for the filing described in ¶ 162 of Decision No. C17-0750.

- On June 11, 2018, Boulder and Public Service jointly filed the Third Request for Additional Time, stating that progress had been made with regard to several of the required agreements, but that “several critical sticking points” were yet to be resolved.  Through Decision No. C18-0492-I, issued June 20, 2018, we scheduled a status conference at which Boulder and Public Service were to appear and answer questions regarding the Third Request for Additional Time.

- On June 29, 2018, the status conference was held.  Counsel and representatives for Boulder and Public Service answered questions about the status of the negotiations and their expectation for when the cost agreement(s) would be finalized.  Boulder and Public Service stated that they expected that the cost agreement(s) and agreement(s) granting Public Service permanent access to easements could be filed no later than August 24, 2018.  Additionally, at the status conference, Boulder’s Counsel made an extemporaneous request to file the corrected asset list separately from the agreements.

Through Decision No. C18-0557-I, issued on July 16, 2018, the Commission set August 24, 2018 as the filing date for the cost agreements and the permanent easement agreement.  Decision No. C18-0557-I also required the Parties to inform the Commission by August 24, 2018 when the corrected asset list would be filed.  Decision No. C18-0557-I also allowed for the corrected asset list to be filed separately from the agreements.

### Joint Motion for Extension of Time to File a Cost Agreement and Permanent Easement Agreement and Joint Motion for Additional Time to File a Corrected List of Assets

- On August 24, 2018, Boulder and Public Service filed a Joint Motion for Extension of Time to File a Cost Agreement and Permanent Easement Agreement (Fourth Request for Additional Time).  In the Fourth Request for Additional Time, the Parties state that they have negotiated a cost agreement and have completed a permanent easement agreement but that they have yet to obtain all approvals of those agreements from the Boulder City Council and from Public Service.  They state, however, that they believe those approvals will be obtained so that the Agreements could be filed on or before September 28, 2018.

- Also on August 24. 2018, Boulder and Public Service filed a Joint Motion for Extension of Time to File Corrected List of Assets, requesting an extension to October 26, 2018 for filing the corrected asset list.  The Parties state that they have resolved the issue of ownership of poles in the list of assets, and that they are working on changes identified in the scopes of work, updating the assets necessary to serve city customers, and identifying the real property interests associated with the assets Boulder seeks to acquire.

### Findings and Conclusions

- Boulder and Public Service assert that they have negotiated the cost agreement and the permanent easement agreement, but the agreements have yet to receive final approval by the Boulder City Council and Public Service.  The Parties state they anticipate approval of each agreement will be received so the agreements can be filed by September 28, 2018.

- Boulder and Public Service state the corrected asset list can be filed by October 26, 2018.

- Decision No. C17-0750 required, as a condition, of approval of Boulder’s Third Supplemental Verified Application that the cost agreement, permanent easement agreement, and corrected asset list be filed simultaneously.  Decision No. C18-0557-I vacated that requirement.

- We find the Parties have shown good cause for an extension of time for the filing of the cost agreement, permanent easement agreement, and corrected asset list.

- The single-filing requirement of ¶163 of Decision No. C17-0750 initiated a 
30-day period during which parties could review the agreements and the corrected asset list and, if necessary, request a hearing.  Given the proximity in time of the requested filing dates in the Fourth Request for Extension of Time and the Joint Motion for Extension of Time to File Corrected List of Assets, a single filing date for the agreements and the corrected list of assets will allow administrative efficiency and allow the compliance review procedures set forth in Paragraph 163 of Decision No. C17-0750.

- We find that an extension to October 26, 2018 for a single filing of the cost agreement, the permanent easement agreement, and the corrected list of assets is appropriate.

- We also acknowledge that the Parties must submit these filings for approval prior to the commencement of any condemnation proceeding.  We find that information about modifications to Boulder’s schedule with regard to the condemnation process would be helpful and therefore direct Boulder to file a statement by October 26, 2018 as to when it anticipates a condemnation process would begin.

## ORDER

### It Is Ordered That:

- The Joint Motion for Extension of Time to File a Cost Agreement and Permanent Easement Agreement filed by the City of Boulder and Public Service Company of Colorado (Public Service) on August 24, 2018 is granted with modifications, as discussed above.

- The Joint Motion for Extension of Time to File Corrected List of Assets filed by the City of Boulder and Public Service on August 24, 2018 is granted.

- By October 26, 2018, the City of Boulder shall file an agreement regarding permanent easements for Public Service to serve its customers in Boulder after separation of Public Service and the City of Boulder’s electric distribution systems, an agreement regarding payment for separation of the electric distribution systems, and a corrected list of assets outside the substations, as required in Decision No. C17-0750.

- By October 26, 2018, the City of Boulder shall file a statement indicating when it anticipates commencing a proceeding regarding condemnation of assets that it seeks to acquire.

- Response time is waived.

This Decision is effective upon its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
August 29, 2018.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ FRANCES A. KONCILJA ________________________________ WENDY M. MOSER ________________________________ Commissioners |
| --- | --- |