BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

Docket No. 97I-198T

________________________________________________________________________________

IN THE MATTER OF THE INVESTIGATION INTO U S WEST COMMUNICATIONS, INC.’S COMPLIANCE WITH §271(C) OF THE TELECOMMUNICATIONS ACT OF 1996

______________________________________________________________________________

Docket No. 99A-577T

IN THE MATTER OF US WEST COMMUNICATIONS, INC.’S STATEMENT OF GENERALLY AVAILABLE TERMS AND CONDITIONS

##### ICG’S COMMENTS FOR THE SECOND WORKSHOP

______________________________________________________________________________

ICG Telecom Group, Inc. (“ICG”) submits these comments in advance of the Second Workshop to be conducted August 1 - 3, 2000, on the topics of interconnection, collocation, and resale.  ICG’s Comments address only the issue of collocation.

The purpose of these comments is to describe ICG’s actual experiences in establishing collocations with U S West.  ICG is a facilities-based Competitive Local Exchange Carrier (CLEC) with significant business operations and customers in Colorado.  ICG currently has five switches in service in Colorado with additional switches planned in the near term future.  As of July 1, 2000, ICG had established nine (9) virtual collocations and 13 physical collocations in U S West’s central offices in Colorado.

ICG’s experience in establishing collocations at U S West’s Central Offices in Colorado has been characterized by frustration and delay.  ICG’s planning and engineering staff work with the  U S West account team to implement collocations.  It is common to not see any progress from week-to-week on simple issues such as determining whether the collocation equipment has been received, whether cables have been ordered or installed, and many other “nuts and bolts” issues.

The collocation application process itself is long and difficult.  The application form is 16 pages in length and difficult to complete in a fashion that clearly indicates time frames and responsibilities.  Oftentimes, clarifications to the application form require a complete re-submittal, payment of additional fees, and restarting time clocks.

Although U S West claims that its standard interval from installation to completion is 90 days, ICG’s experience is that the collocation process takes, on average, more than one year.  Some of ICG’s ordered collocations are still incomplete after two years.

U S West projects that it will take 10 days from the time U S West receives an application to the date the feasibility report is submitted to the customer.  Based on ICG’s actual experience, the amount of time has been 25 days, not 10 days.  From the date of feasibility to the date a quote is provided, U S West claims an interval of 35 days.  Based on ICG’s actual experience, the actual average number of days is 60.

ICG has repeatedly experienced problems in physical collocation situations with fiber patch cords.  At times, U S West personnel would advise ICG that certain patch cords were installed but when ICG’s test crew would go to the location, they would find that the patch cords had never been installed.  Obviously, this introduced further delay and expense of dispatching a crew to test fiber patch cords that had never been installed.

ICG has attempted to expedite installation of collocations.  The attempts, however, have been futile.  In two cases, U S West personnel told ICG that an established schedule could not be changed or expedited.  U S West claimed a lack of installation contractors prevented any scheduled changes.  ICG sought to swap jobs with other installation teams but was refused.  ICG asked if it could provide its own installers to work on these collocations but that offer was refused by U S West.

The delay in completing collocations extends to both physical and virtual collocations.  With virtual collocations, CLECs have very little control over the planning, engineering, installation, operations and maintenance of these collocations.  ICG’s experience is that virtual collocations are problem-ridden and delay prone, prompting ICG to seek conversion of virtual collocations to cageless physical collocations.

ICG has also been repeatedly frustrated and delayed in its attempts to convert virtual collocations to cageless physical collocations.  While this should be a relatively simple process, in fact, it has been a difficult, expensive and time-consuming process.  For example, after a request for conversion from a virtual to a physical collocation, U S West stated that first an audit must be done to determine where the equipment was located and to determine whether the equipment was in a bay that did not have any other carrier’s equipment in it.  Then, U S West stated that if the equipment was located in a bay with another carrier’s equipment, the virtual collocation could not be converted to a cageless physical collocation.  On the other hand, if the virtually collocated equipment was in a bay by itself, U S West required ICG to go through the application process to place new equipment in the cageless lineup so that it could be differentiated from other virtual collocated equipment.  Furthermore, U S West claims that conversion of a virtual collocation to a cageless physical collocation requires a change in the CLLI code.  Each CLLI code change requires additional time and paperwork processing, creating unnecessary expense and delay.

It has been ICG’s experience that collocations with U S West are far more expensive than  any of the other RBOCs.   ICG has experience in obtaining collocations from BellSouth, Ameritech, and PacBell.  The cost requirements imposed by U S West far exceed the costs to establish collocations in any other regions.

ICG contends that U S West has not yet fulfilled its requirements to offer effective collocation to CLECs in a manner that complies with the Telecommunications Act of 1996.

DATED this 11th day of July 2000

Respectfully submitted,

_________________________________

Craig D. Joyce

WALTERS & JOYCE, P.C.

2015 York Street

Denver, CO 80205

303-322-1404

CERTIFICATE OF SERVICE

I hereby certify that on July 11, 2000, the original and five (5) copies of the foregoing ICG’s COMMENTS  FOR THE SECOND WORKSHOP were filed with:

Bruce Smith

Executive Director

Colorado Public Utilities Commission

1580 Logan Street, OL-2

Denver, CO 80203

and copies were placed in the U S Mail, postage prepaid, addressed to the following:

Joseph Molloy

Colorado Public Utilities Commission

1580 Logan Street, OL-2

Denver Colorado 80203

Mana Jennings-Fader

Office of the Attorney General

1525 Sherman Street, 5th Floor

Denver, Colorado 80203

and copies were served by electronic mail on the participants in these dockets on the most current electronic mail service list maintained and published by the Commission.

/s/ Craig D. Joyce