# Decision No. R12-0425

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 10A-286G

IN THE MATTER OF THE application of atmos energy corporation for an order approving natural gas demand side management plan.

RECOMMENDED DECISION OF
ADMINISTRATIVE LAW JUDGE
KEITH J. KIRCHUBEL
GRANTING JOINT MOTION; APPROVING SETTLEMENT; AND CLOSING DOCKET

Mailed Date:  April 23, 2012

## statement

- On September 1, 2011, Applicant Atmos Energy Corporation (Atmos) filed a Petition, together with supporting testimony of Mr. Kevin Kerrigan, seeking leave to modify its 2011 Demand Side Management (DSM) Plan.  Atmos’ 2011 DSM Plan was approved by Decision No. C10-0723, issued on July 14, 2010.

- The Commission gave notice of the Petition on September 8, 2011.

- On October 19, 2011, the Trial Staff of the Colorado Public Utilities Commission (Staff) filed a Notice of Intervention as of Right and Entry of Appearance through counsel.

- On October 26, 2011, disposition of this matter was referred to the undersigned Administrative Law Judge (ALJ) by minute order of the Commission.

- Pursuant to Decision No. R11-1287-I, issued November 8, 2011, a procedural schedule was established for this Docket, including a deadline for Staff to pre-file written Answer Testimony on December, 16, 2011, and a hearing date scheduled on January 19, 2012.

- On December 15, 2011, the parties filed a Joint Motion to Vacate the date for filing Answer Testimony based on the progress of settlement discussions then under way.  Pursuant to Decision No. R11-1363-I, issued on December 16, 2011, the deadline for filing Answer Testimony was delayed until December 22, 2011.

- On December 22, 2011, the parties filed a Stipulation and Settlement Agreement (Settlement Agreement) accompanied by a Joint Motion for Approval of the Settlement Agreement (Settlement Motion).  The Settlement Agreement sets forth the terms under which Atmos and Staff resolved all the outstanding issues in this Docket.  It also addresses the settlement of the outstanding issues in two other dockets involving very similar subject matter.

- Pursuant to Decision No. R12-0154-I, issued February 13, 2012, a hearing was scheduled to receive evidence in support of the Settlement Motion as it pertained to each of the Associated Dockets.

- On February 23, 2011, the ALJ convened the above-referenced hearing related to the pending Settlement Motion.  Mark Davidson of the firm Holland and Hart appeared as counsel for Atmos.  First Assistant Attorney General Anne Botterud appeared as counsel for Staff.  Atmos presented the testimony of Mr. Kevin Kerrigan.  Staff presented the testimony of Mr. Keith Hay.  Mr. Kerrigan’s pre-filed written testimony was admitted as Hearing Exhibit No. 1.  The Settlement Agreement was admitted as Hearing Exhibit No. 2.  
An Impact Evaluation of Natural Gas DSM Programs dated April 12, 2011, was admitted as Hearing Exhibit No. 4.  At the conclusion of the hearing, the ALJ took the matter under advisement.

- On March 23, 2012, the ALJ sought clarification from Atmos and Staff regarding a reference found in Hearing Exhibit No. 2 in the first paragraph under the heading III.C.  This provision purports to establish the “exact dollar amount” agreed upon by the parties by referencing the internal exhibits included with the Settlement Agreement.  However, the ALJ determined that the reference was not sufficiently clear in that various dollar amounts are shown in the internal exhibits to Hearing Exhibit No. 2.

- On March 27, 2012, Atmos filed a Statement Responding to the Request for Clarification identifying as the basis for the settlement the amount listed as “Revised 2011 Program Expenditure Projection” on internal exhibit 1 to Hearing Exhibit No. 2.

- In accordance with, and pursuant to § 40-6-109, C.R.S., the ALJ transmits to the Commission the record and exhibits of the proceeding together with a written recommended decision.

## Discussion and Conclusions

- Atmos provides natural gas sales and transportation service to over 110,000 customers within the State of Colorado.

- The Commission’s Rules Regulating Gas Utilities and Pipeline Operators, at 4 Code of Colorado Regulations (CCR) 723-4-4750, et seq, require each gas utility to file a DSM Plan for approval by the Commission.  As noted above, Atmos submitted a plan that was approved July 14, 2010, for calendar year 2011 pursuant to Decision No. C10-0723.

- In the approved 2011 DSM Plan, Atmos included a budget of $588,629 for the calendar year.

- In implementing its DSM Plan, Atmos acted in collaboration with other local distribution companies who identified this joint effort by the name Partners in Energy Savings (PIES).  PIES, in turn, selected a contractor to perform various functions of its DSM rebate program.  This contractor was Electric, Gas and Industries Association (EGIA) of Sacramento, California.

- Atmos agreed that customer participation in the DSM program could be maximized by allowing rebates for energy-saving measures to be grouped into a general budget category.  This process was intended to permit greater customer participation on the theory that budgeted dollars grouped into a general category could be shifted to support those DSM measures that were generating more rebate requests than the segregated budgets for such measures could support.

- Based on its past experience with DSM programs, Atmos developed the 2011 budget with projected participation by 185 customers in its insulation rebate measure.  Starting in the fourth quarter of 2010, two contractors in Colorado started an aggressive campaign to sign up customers for insulation installation and rebates.  This resulted in 731 customers participating in the insulation rebate program in 2011.

- As a consequence, during 2011, EGIA processed customer rebate requests which generated invoices to Atmos well in excess of the approved budget amount.  Although Atmos (and each of the other PIES participants) was responsible for monitoring the program to ensure that it complied with the approved DSM Plan, the creation of a general budget category and the manner of invoicing by EGIA allowed this overrun to go undetected by Atmos for a period of several months.

- Atmos became aware of the increase in participation in late 2010.  
Once it determined that the rebate applications in process for the insulation program would exhaust the entire 2011 DSM budget in the first quarter of 2011, Atmos acted to halt the insulation program and notified insulation contractors and customers that no further rebates for insulation were available.

- Atmos characterizes this overrun as an aberration and seeks $276,271 in additional funds to enable it to meet its DSM program goals for 2011.

- The proposed increase in the 2011 DSM program budget is predicted to have an impact on the monthly bills of residential customers in the range of 21 to 25 cents per month.  
On average, this impact amounts to less than one-half of 1 percent of a residential customer’s monthly bill.

- The rate impact of the proposed increase is smaller for commercial customers given that the majority of DSM program benefits are realized by the residential rate class.  The projected increase for the commercial class is in the range of 2 to 3 cents per month.

- As part of its Application, Atmos agreed to institute new controls to prevent any recurrence of the overrun experienced in the 2011 program year.  Mr. Kerrigan established that all rebate requests are now submitted through an automated system that tracks the number of subscriptions in real time.  Customers can either access the program via an online portal or by contacting EGIA whose representatives then access the same portal.  Either way, each new rebate subscription is confirmed to the customer and accounted for against a set maximum.

- Atmos will provide EGIA with the annual budget for each measure approved in the current DSM Plan.  Customer access to rebate funds will be limited to the budgeted amount for each measure and not from a grouped general budget category.

- The automated system gives Atmos the ability to track progress of the various DSM measures without the lag time of waiting for paper forms to be submitted by contractors and/or customers or batches of invoices to be processed by EGIA.  In the event that the maximum number of subscriptions is reached, then the system will not authorize further rebates.

- Atmos will, however, retain the flexibility to move budgeted dollars among various measures as permitted in the approved DSM plan in order to maximize participation and energy savings.

- In addition, Atmos has instituted a process whereby its DSM program staff and EGIA communicate regularly about the functionality of the automated system and the progress of the DSM program overall.

- These measures instituted in response to the overrun in the 2011 program year should effectively prevent such a problem from recurring in the future.

- Atmos has not requested any additional funds for the DSM budgets approved for 2012 or 2013 indicating the company’s own confidence in the new controls.

- Atmos will provide Staff with quarterly status reports through December 31, 2013 that will include the following information:  annual budget by measure; dekatherm savings goal by measure; quarterly rebate spending by measure; and dekatherms saved by measure.  These quarterly reports will be in addition to the annual report required by 4 CCR 723-4-4754 and will be submitted within 30 days of the end of each quarter.

- The ALJ finds that the rebates authorized during the 2011 program year, including the overrun occasioned by the subscription of far more insulation upgrades than forecast, were paid to achieve energy savings and that these funds were spent in a manner consistent with the long-range energy reduction goals expressed in § 40-3.2-103, C.R.S., and the Commission’s Rules regarding gas DSM programs, 4 CCR 723-4-4750, et seq.

- Despite the fact that the budget overrun was unauthorized at the time it happened, the ALJ finds good cause to approve the additional budget amounts now.  This conclusion is supported by the previous finding that the additional dollars were not wasted or used for an improper purpose.  They were used for projects that, while excessive in number, achieved the energy savings goals of the DSM programs.  Nor did any party appear in opposition to the Application and the proposed Settlement.  Additionally, the ALJ finds that controls instituted by Atmos and Staff are sufficiently likely to prevent the same problem recurring in the future.  Lastly, the bill impact of the additional budget amounts is not unreasonable given that the overrun was actually used for energy-saving projects.

- For the foregoing reasons, the ALJ finds the terms of the settlement to be fair, just, and in the public interest.

- Pursuant to § 40-6-109(2), C.R.S., the ALJ recommends that the Commission enter the following order.

## order

### The Commission Orders That:

- The Joint Motion for Approval of Stipulation and Settlement Agreement filed on December 22, 2011, is granted.  The Stipulation and Settlement Agreement (Settlement Agreement) filed on December 22, 2011, is approved.  A copy of the Settlement Agreement, including its own appendices, is attached hereto as Appendix A.

- The Settlement Agreement is incorporated by reference and made an order of the Commission as if fully set forth herein.  All Parties shall comply with all terms thereof.

- The revised budget of $864,900 for the 2011 gas demand side management program of Atmos Energy Corporation (Atmos) is approved.

- In addition to any reports required by rule or other Commission Orders, Atmos shall submit quarterly status reports, as discussed above and provided for in the Settlement Agreement.

- Atmos is authorized to implement changes in the gas demand side management cost adjustment rates as necessary to recover the approved gas budget set forth in Ordering Paragraph No. 3, above.

- Atmos shall file, on not less than one day’s notice to the Commission, tariff sheets changed as necessary to conform to the terms of the Settlement Agreement and this Recommended Decision.

- Docket No. 10A-286G is now closed and all proceedings are vacated.

- This Recommended Decision shall be effective on the day it becomes the Decision of the Commission, if that is the case, and is entered as of the date above.

- As provided by § 40-6-109, C.R.S., copies of this Recommended Decision shall be served upon the parties, who may file exceptions to it.

  - If no exceptions are filed within 20 days after service or within any extended period of time authorized, or unless the decision is stayed by the Commission upon its own motion, the recommended decision shall become the decision of the Commission and subject to the provisions of § 40-6-114, C.R.S.

  - If a party seeks to amend, modify, annul, or reverse basic findings of fact in its exceptions, that party must request and pay for a transcript to be filed, or the parties may stipulate to portions of the transcript according to the procedure stated in § 40-6-113, C.R.S.  If no transcript or stipulation is filed, the Commission is bound by the facts set out by the administrative law judge and the parties cannot challenge these facts.  This will limit what the Commission can review if exceptions are filed.

- If exceptions to this Decision are filed, they shall not exceed 30 pages in length, unless the Commission for good cause shown permits this limit to be exceeded.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO KEITH J. KIRCHUBEL ________________________________ - Administrative Law Judge |
| --- | --- |

As explained in Decision No. R11-1207-I, the Atmos filing was denominated as an Application pursuant to 4 Code of Colorado Regulations 723-4-4002(a)(XIV).

Docket No. 10A-278G (Eastern Colorado Utility Company) and Docket No. 11A-746G (SourceGas Distribution, LLC).  The three dockets will be referenced collectively in this Decision as the “Associated Dockets.”  While the Associated Dockets were not formally consolidated, all were transferred to the ALJ for consideration of the collective settlement.

Mr. Kerrigan is the manager of sales for the Colorado division of Atmos.

Mr. Hay is a Rate Financial Analyst for the Commission (Staff).

The Settlement Agreement includes its own internal exhibits numbered 1 through 4.  Internal exhibit no. 1 pertains to the Atmos Application.

This amount is $864,900.00, which is an increase of $276,271.00 over the amount approved for the 2011 DSM budget.

PIES represented approximately 200,000 natural gas customers in Colorado.

A study conducted on behalf of Atmos verified that this insulation upgrade work was actually performed and resulted in the energy savings at the heart of DSM programs generally.  Hearing Exhibit No. 4.

i.e., not just the home insulation measure budget.

Such shifting is only permissible between measures targeted to the same customer class (i.e., residential).