# Decision No. C08-0361

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 05A-066R

IN THE MATTER OF THE APPLICATION OF union pacific railroad company, for authority to construct a grade separation at the crossing of union pacific railroad company and timberhouse road (crossing No. DOT 924 190J) in winter park, state of Colorado.

ORDER requiring parties to file a joint SETTLEMENT resolution with the commission

Mailed Date:  April 4, 2008

Adopted Date:  April 2, 2008

## BY THE COMMISSION

### Statement

- This matter comes before the Commission for consideration of Motion to Require Xcel Energy to Relocate its Gas Line on an Expedited Basis (Motion) filed by Union Pacific Railroad Company (Union Pacific) on March 14, 2008.

- In its Motion, Union Pacific explains that in 2005, it submitted an Application to the Commission to build a grade separation in Winter Park, Colorado.  In August 2005, an administrative law judge approved a stipulation between Union Pacific, the Colorado Department of Transportation (CDOT), and the City of Winter Park, Colorado (Winter Park).  Public Service Company of Colorado (Public Service) was notified of the pleadings in the matter and never intervened; thus, Public Service was not part of the settlement.

- Since the approved settlement, Union Pacific contends that Union Pacific, CDOT, and Winter Park complied with steps necessary to complete this separation.

- Union Pacific asserts that in order to complete the grade separation project, Public Service must move a gas line adjacent to the proposed grade separation.  Union Pacific states that it has made numerous attempts to gain Public Service's cooperation on this matter without success.  Therefore, Union Pacific asks that the Commission enter an order requiring Public Service to relocate its gas line on an expedited basis but no later than April 30, 2008.

- On March 31, 2008, Public Service filed its response to the Motion.  In its response, Public Service states that it agrees with the general factual background provided by Union Pacific.

- Public Service also asserts that appropriate actions have been taken since the Motion was filed.  They contend that they are confident that the work Union Pacific requests will be completed by April 30, 2008 and asks the Commission to deny the Motion as moot.

- Now being fully advised in the matter, we find that we will not rule on the Motion at the present time.

- We find that it is appropriate to require Union Pacific and Public Service to file a Joint Resolution Statement with the Commission by 12:00 p.m. on Monday, April 7, 2008.  The Joint Resolution Statement must discuss the status of the communications between Public Service and Union Pacific and the steps Public Service is taking to remove its gas line from the grade separation area by April 30, 2008.

- In the Commissioners’ Weekly Meeting on Wednesday, April 9, 2008, we will address this Motion based on our receipt of the Joint Resolution Statement.

## ORDER

### The Commission Orders That:

- Union Pacific Railroad Company and Public Service Company of Colorado must file a Joint Resolution Statement by 12:00 p.m. on Monday, April 7, 2008, pursuant to the discussion above.

- We will reexamine the Motion to Require Xcel Energy to Relocate its Gas Line on an Expedited Basis filed by Union Pacific Railroad Company at the weekly meeting on April 9, 2008.

- This Order is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
April 2, 2008.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO RON BINZ ________________________________ JAMES K. TARPEY ________________________________ MATT BAKER ________________________________ Commissioners |
| --- | --- |

/tmp/in/input.doc:SRS