# Decision No. C09-1152

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 08A-527R

IN the matter of the application of the city of grand junction, 250 north 5th street, grand junction, colorado 81501, for authority to construct a new bridge at 29 road over the union pacific railroad track and yard in grand junction, colorado.

COMMISSION ORDER 
GRANTING EXTENSION OF TIME

Mailed Date:  October 8, 2009

Adopted Date: October 7, 2009

## BY THE COMMISSION

### Statement

- This matter comes before the Commission for consideration of the Unopposed Motion to Modify Commission Decision No. R09-0682 (Motion) filed by the City of Grand Junction (Grand Junction) on September 29, 2009.

- By Decision No. R09-0682, the Commission ordered Grand Junction to file a signed copy of the construction and maintenance agreements by September 30, 2009.

- Grand Junction states that it has been working diligently with the Union Pacific Railroad Company on completing the construction and maintenance agreement, but that due to unforeseen complications associated with the land valuation process, the agreement is not complete and will take additional time to process.

- Grand Junction requests an extension of time to December 1, 2009 to file the signed construction and maintenance agreement.

- Our review of the record shows that the application was for a new bridge structure at a location where an at-grade crossing currently does not exist.  We do not believe any safety issues will result from extending the time for the filing of the construction and maintenance agreement or the subsequent delay to starting the construction of the bridge.  We will therefore grant an extension of time to December 1, 2009 for the parties to file the signed construction and maintenance agreement.

- We will also waive response time to the Motion given that no party to this matter objects to the request.

- Now being duly advised in the matter, the Commission finds good cause has been stated and will grant the motion pursuant to the discussion above.

## ORDER

### The Commission Orders That:

- The Unopposed Motion to Modify Commission Decision No. R09-0682 filed by the City of Grand Junction is granted.  The City of Grand Junction shall be permitted to file signed copies of the construction and maintenance agreements for this project by December 1, 2009.

- The Commission waives response time to the motion.

- This Order is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
October 7, 2009.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO RONALD J. BINZ ________________________________ JAMES K. TARPEY ________________________________ - Commissioners COMMISSIONER MATT BAKER ABSENT. |
| --- | --- |

/tmp/in/input.doc:SRS