Decision No. C10-0530

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 10M-206E

IN THE MATTER OF THE DESIGNATION OF ELECTRIC UTILITY TRANSMISSION FACILITIES AND ELECTRIC UTILITY GENERATION FACILITIES FOR WHICH AN APPLICATION TO OBTAIN A CERTIFICATE OF PUBLIC CONVENIENCE AND NECESSITY IS REQUIRED OR THE FILING OF A FORMAL DETERMINATION THAT NO CERTIFICATE IS REQUIRED.

order PROVIDING notice of
filing AND ESTABLISHING
OPPORTUNITY TO FILE COMMENTS

Mailed Date:  June 1, 2010

Adopted Date:  May 26, 2010

## BY THE COMMISSION

### Statement

- Rule 3206(c) of the Commission’s Rules Regulating Electric Utilities, 4 Code of Colorado Regulations 723-3, requires each Colorado electric utility to file with the Commission, no later than April 30 of each year, information on its proposed new construction or extensions of transmission facilities for the next three calendar years.

- Rule 3206(f) provides that the Commission will give notice of the filing of data to all those who, in the opinion of the Commission, are interested persons, firms, or corporations.  Any interested person, firm, or corporation may file comments regarding the projects identified by the information filed with the Commission within 15 days of the filing date of the required information.  Because in this instance, that 15-day period has elapsed for some of the data, the Commission will waive that requirement and instead allow comments to be filed within 15 days after the effective date of this Order.

- The following utilities have filed information on proposed construction projects as listed:

- INVESTOR-OWNED UTILITIES

- Black Hills/Colorado Electric Utility Company, L.P. (formerly Aquila, Inc.)

1.	Portland-West Station #2 115kV Transmission Line and Associated Substation   Expansion/Upgrades – new project.

- This 20-mile 115kV transmission line project will improve reliability in the Canon City area and was identified in Black Hills/Colorado Electric Utility Company, L.P’s (BHCE) 2009 SB-100 report.  The in-service date is 2013 at a cost of $12.5 million.

2.	Pueblo-Hyde Park-West Station 115kV Transmission Line Rebuild – new project.

- This 4.5-mile 115kV transmission line rebuild will increase the line rating for improved reliability in the Pueblo area and was identified in BHCE’s 2009 SB-100 report. The in-service date is 2012 at a cost of $2.7 million.

3.	Greenhorn-Reader 115kV Transmission Line Rebuild – new project

- This five-mile 115kV line rebuild will improve reliability in the Pueblo area and was identified in BHCE’s 2009 SB-100 report.  The in-service date is 2014 at a cost of $3.0 million.

- 4.	Reader 115/69 kV Transformer Replacement – new project.

The existing 41 MVA units will be replaced with 80 MVA units.  The additional transformation capacity will improve reliability in the Pueblo area.  The in-service date is 2013 at a cost of $6.5 million.

5.	Portland-West Station #2 115kV Transmission Line and Associated Substation Expansion/Upgrades – new project.

- This 20-mile 115kV transmission line project will improve reliability in the Canon City area and was identified in BHCE’s 2009 SB-100 report.  The in-service date is 2013 at a cost of $12.5 million.

- 6.	Pueblo-Hyde Park-West Station 115kV Transmission Line Rebuild – new project.

- This 4.5-mile 115kV transmission line rebuild will increase the line rating for improved reliability in the Pueblo area and was identified in BHCE’s 2009 SB-100 report. The in-service date is 2012 at a cost of $2.7 million.

7.	Greenhorn-Reader 115kV Transmission Line Rebuild – new project

- This five-mile 115kV line rebuild will improve reliability in the Pueblo area and was identified in BHCE’s 2009 SB-100 report.  The in-service date is 2014 at a cost of $3.0 million.

8.	Reader 115/69 kV Transformer Replacement – new project.

- The existing 41 MVA units will be replaced with 80 MVA units.  The additional transformation capacity will improve reliability in the Pueblo area.  The in-service date is 2013 at a cost of $6.5 million.

- 9.	Overton 115-13.8kV Substation, in-service date of 2013, no certificate of public convenience and necessity (CPCN) required per Decision No. C07-0553.

10.	La Junta-Tri-State Interconnect, in-service date is 2013, no CPCN required per Decision No. C09-1240.

- 11.	Baculite Mesa (formerly Airport Tap) 115kV Substation Expansion, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- 12.	West Station-Baculite Mesa (formerly Airport Tap) double circuit 115kV line, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- 13.	West Station 115 kV Substation Expansion, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- 14.	Nyberg 115kV Substation, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- 15.	Baculite Mesa (formerly Airport Tap)–Nyberg 115kV Line Rebuild, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- 16.	Baculite Mesa (formerly Airport Tap)–Airport Memorial 115kV Line Rebuild, in-service date is 2011, no CPCN required per Decision No. C09-1240.

- Public Service Company of Colorado (PSCo)

- 1.	Parachute-Cameo 230kV Transmission Line – new project.

- This project proposes to construct approximately 31 miles of 230kV transmission between the Parachute and Cameo Substations on a new right-of-way.  The project will support the Cameo load area that will be degraded by the retirement of the Cameo Generation Station in December 2010.  The new line will be used to serve the Debeque and Una loads that are presently served by the RifleCU-Cameo 69kv line, part of the RifleUte-Grand JunctionUte 69kv line.  A portion of the Cameo-RifleCu 69kV line (between the Cameo Substation and the Grand Valley 69kV Substation) will be removed from service.  The in-service date is 2013-2014 at a cost of $48.5 million.

2.	Lamar-Front Range 345/500kV and Lamar-Vilas 230/345kV Transmission Project – new project

- The Lamar-Front Range345/500kV (345kV operation/500kV construction) segment of this project consists of building two 345/500kV lines from the Lamar Substation in southeast Colorado – 1) one to Comanche Substation in Pueblo, Colorado, and 2) the other one to Burlington-Big Sandy-Missile Site near Deer Trail, Colorado.  The project is proposed in accordance with Senate Bill 07-100 to facilitate 800-1000 MW of generation resources in Energy Resource Zones (ERZ) 2 and 3.  It is a joint participation project between PSCo and Tri-State Generation and Transmission Association, Inc. (Tri-State).  The Lamar-Vilas 230/345kV (230kV operation/345kV construction) segment of this project consists of building about 60 miles of line from Lamar to Vilas Substation in southeast Colorado.  This is also a Senate Bill 07-100 project designed to transport wind generation in ERZ 3 (Baca County) to the Front Range load centers.  Tri-State may also be a participant in this project.  Both these projects may be integrated with the proposed High Plains Express initiative.  The Lamar Front Range cost is $287 million and the Lamar-Vilas cost is $36.7 million with an in-service date of 2016-2017.

- 3.	Rifle (Ute)-Story Gulch 230kV Transmission Line Project – new project.

- This project consists of a new Story Gulch 230kV Substation and about 25 miles of 230kV single-circuit transmission line from Story Gulch Substation to the RifleUte Substation.  The Story Gulch Substation would be located just south of the Rio Blanco-Garfield County line and about seven miles north of the PSCo Middle Fork Substation.  The substation and line are needed to serve future large PSCo customer loads in the Piceance Basin.  The in-service date is June 2013 at a cost of $24.14 million.

4.	RTD FastTracks-East Corridor Project (Underground Line Relocation) – new project.

- Regional Transportation Denver (RTD) FastTracks proposes to build an electric commuter train to the Denver International Airport.  To accommodate this project, a road owned by the City of Denver will be relocated.  The new road will be laid on top of the North-California underground (UG) section of the Cherokee-California 115kV line and the North-Capitol Hill UG section of the Cherokee-Capitol Hill 115kv line.  The impacted lines include 3500 feet per circuit of the 3-phase oil filled underground lines.  In order to allow future access to these lines, the impacted section will be rerouted. During the relocation, California Substation will be fed radially from Harrison Substation.  To provide backup to California Substation during the line relocation and to provide permanent system reliability to the underground network, an additional feed or “Y” splice will be constructed by tapping the North-Capitol Hill UG 115kV line with an 0.88 mile UG cable to California Substation.  The in-service date is November 2011 at a cost of $8.77 million.

- 5.	Barker Substation (Distribution) – new project.

- This project proposes to build a 230-13.8kV Barker substation near 20th Avenue and Blake Street across from Coors field in Denver, Colorado.  PSCo will install two 50 MVA 230-13.8kv transformers at the substation.   Barker Substation will be fed by 2000 feet of a double circuit (in-and-out) underground 230kV transmission line between Lacombe and Barker Substations. This project is required to supply the continued load growth in the Lower Downtown area and to eliminate overloads on the ninth network in Denver.  The in-service date is May 2015 at a cost of $16.4 million.

- 6.	Brantner Substation (Distribution) - new project.

- This project proposes to build a new 115-13.8kV Bratner Substation near 128th Avenue and Holly Street in Thornton, Colorado.  The transmission portion of this project consists of about one mile of in-and-out interconnection tap of the existing Fort Lupton-Cherokee 115kV line.  The substation will be built to accommodate two 50 MVA transformers with one installed initially.  The project is needed to meet the increasing load growth in Thornton, Colorado.  The in-service date is June 2014 at a cost of $1.76 million.

- 7.	Carey Substation (Distribution) – new project.

- This project proposes to build a new 230-13.8kV Carey Substation.  The new substation will tap Platte River Power Authority’s Ault-Timberline 230kV line with a three-mile double circuit 230kV line with an in-and-out termination.  The substation will be a joint project among PSCo, Tri-State, and Poudre Valley REA.  The substation will be built to accommodate one transformer for PSCo and one for Poudre Valley with PSCo’s 28 MVA transformer installed initially.  The in-service date is May 2014 at a cost of $9.0 million to be shared amongst the joint owners.

- 8.	Eboda Substation (Distribution) – new project.

- This project proposes to build a new 230-13.8kV Eboda Substation east of the existing Adobe Substation in western Colorado.  The substation will be fed by a tap of the Uintah-Adobe-Horizon-Grand Junction 230kV transmission 230kV line.  The substation will be built to accommodate three 230-13.8kV 28 MVA transformers with one transformer installed initially.  The in-service date is December 2011 at a cost of $3.0 million.

- 9.	Wilson #1 Substation (Distribution) – new project.

- This project proposes to build a new 115-13.8kV Wilson Substation, near Wilson Avenue and Larimer County Road 28 near Loveland, Colorado.  The substation will be fed by an in-and-out tap of Platte River Power Authority’s Horseshoe-West 115kV transmission line.  The substation will be built for two 14 MVA transformers with one being installed initially.  This project is needed to meet the load growth around the Loveland area.  The in-service date is May 2014 at a cost of $3.37 million.

- 10.	University #3 Substation (Distribution) – new project.

- This project proposes to install a third 115-13.8kV 50 MVA transformer at the University Substation.  The transformer is needed to avoid overloading the existing transformers under system intact conditions and to avoid shedding 15 MVA with an N-1 condition.  The substation will be expanded to accommodate the new transformer.  The in-service is October 2012 at a cost of $0.28 million.

- 11.	Ault-Cherokee 230kV Transmission Line Project – new project.

- This project proposes to build 85 miles of 230kV transmission line from the Ault Substation to the Cherokee Switchyard.  The line will be built in two sections.  The first section will be a 59-mile single circuit 230kV line from Ault Substation to just outside the Fort Lupton Substation.   From this point, the existing Fort Lupton-Cherokee 115kV line will be upgraded to a double circuit 230kV line, with one side operated at 115kV, to complete the Ault-Cherokee 230kV circuit.  This is a Senate Bill 07-100 project capable of transferring 300-600 MW of generation resources in Energy Resource Zone 1 to the Denver Metro area.  The in-service date is 2015-2016 at a cost of $76.6 million.

12.	Bluestone Valley Substation, in-service date of October 2010, no CPCN per Decision No. C09-0681.

13.	San Luis Valley-Calumet-Comanche Transmission Project, in-service June 2013, CPCN application was submitted May 14, 2009, Docket No. 09A-325E.

14.	Poncha Junction 115/230kV Transformer, in-service date is May 31, 2013, no CPCN required per Decision No. C09-0681.

15.	Gunbarrel Substation, in-service May 2009, no CPCN required per Decision No. C08-0676.

16.	Comanche - Reader 115kV Underground Line #2, in-service July 2010, no CPCN required per Decision No. C08-0676.

17.	Kelim 115-1 3.8kV Substation, in-service May 2010, no CPCN required per Decision No. C08-0676.

18.	College Lake 115-1 3.8kV Substation, in-service February 2011, no CPCN required per Decision No. C08-0676

19.	New Castle 115/69-24.9 kV Substation, in-service October 2014, no CPCN required per Decision No. C08-0676.

20.	Missile Site 230kV Switching Station, in-service November 2010, no CPCN required per Decision No. C08-0676.

21.	Missile Site 345kVSubstation, in-service May 2013, a CPCN application, docket No. 10A-240E, was filed April 16, 2010.

22.	Niwot - Gunbarrel Load Service Request (LSR) 230kV Underground Line Project, in-service November 2011, no CPCN required per Decision No. C08-0676.

- 23.	Chambers 230/115kV Transmission Intertie Project, in-service November 2010, CPCN granted per Decision No. C03-1055.

- 24.	Midway-Waterton 345kV Transmission Project, in-service May 2011, Commission Decision No. C09-0775 granted a CPCN.

- 25.	Happy Canyon 115kV, IREA network interconnection, formerly reported by IREA, with an in-service date of May 2011.  No CPCN required per Decision No. C06-761.

- RURAL ELECTRIC ASSOCIATIONS

- Grand Valley Power

1.	Bluestone Valley-Clear Creek 230kV Transmission Line, in-service date of January 2011, no CPCN required per Decision No. C09-0681.

2.	Clear Creek Substation, in-service date of December 2012, no CPCN required per Decision No. C09-0681.

- Intermountain Rural Electric Association, Inc.

- 1.	Phase 1 - Conifer to Shaffers Crossing 115 kV transmission line – new project.

Rebuild and upgrade existing 44 kV transmission line to 115 kV located in Jefferson County between Conifer and Shaffers Crossing along State Highway 285.  This line segment is approximately 7 miles of which 3.5 miles is scheduled to be rebuilt in 2012. Start construction in March 2012; complete/in service, November 2012; estimated cost, $2,800,000.

2.	Phase 2 - Conifer to Shaffers Crossing 115 kV transmission line – new project.

Rebuild and upgrade existing 44 kV transmission line to 115 kV located in Jefferson County between Conifer and Shaffers Crossing along State Highway 285.  This line segment is approximately 7 miles of which 3.5 miles is scheduled to be rebuilt in 2013.  Start construction in March 2013; complete/in service, November 2013; estimated cost, $2,800,000.

- 3.	Happy Canyon Substation (also reported by PSCo), in-service December 2013, no CPCN required per Decision No. C06-0761.

- 4.	Fairplay-Como 115kV Transmission Line, in-service November 2011, no CPCN required per Decision No. C06-0761.

- 5.	Como Substation, in-service November 2011, no CPCN required per Decision No. C07-0553.

- 6.	Wolfensberger-Citadel 115kV Transmission Line, in-service December 2012, no CPCN required per Decision No. C06-0761.

- 7.	Citadel Substation, in-service December 2012, no CPCN required per Decision No. C07-0553.	.

- La Plata Electric Association, Inc.

No filing was made.

- Mountain View Electric Association, Inc.

1.	Limon Substation Expansion, in-service date of September 2010, no CPCN per Decision No. C09-0681.

- 2.	Anderson Substation, in-service August 2009, no CPCN required per Decision No. C06-0761.

- Tri-State Generation and Transmission Association, Inc. (Tri-State)

1.	Crested Butte 1-7.5 MVAR Capacitor Bank Addition – new project.

This project installs a 7.5 MVAR 115kV capacitor bank at the existing Crested Butte Substation.  The project is needed to support voltages in the Crested Butte area with outages of the blue Mesa-Skito 115kvline and the Gunnison–Poncha 115kv line.  The in-service date is 4Q 2010 at a cost of $0.824 million.

2.	Kit Carson Wind Interconnect – new project.

This project interconnects the 51 MW Kit Carson Windpower Wind Farm to Tri-State’s transmission system.  The interconnection facilities will be known as the Landsman Creek Substation and will interconnect with the Big Sandy-Burlington 230kV line about five miles west of the Burlington Substation.   The Landsman Substation will consist of an in-and-out tap to a three breaker ring bus with provision to extend to a breaker-and-a half arrangement.  The in-service is 4Q 2010 at a cost to Tri-State of $3.8 million.

3.	Burlington-Wray 230kV Line – new project.

This project consists of building a new 60-mile single circuit 230kV transmission line from the existing Burlington Substation to the existing Wray Substation, both owned by Tri-State.  This line will complete a 230kv loop through eastern Colorado.  The existing Burlington-Wray 115kV lines rated at 120 MVA is a weak link in eastern Colorado and limits Tri-State’s ability to economically dispatch existing generation in eastern Colorado.  The new 230kv line will parallel the 115kV line correcting this deficiency while also accommodating renewable generation resources in the Wray and Burlington areas.  The line will be built with a 1272 kcmil acsr conductor designed for 100 degrees Centigrade operation, or 1583 amperes.  The in-service date is 4Q 2015 at a cost of $30.1 million.

4. 	La Junta 69kv Tie Line Addition – new project.

This project constructs a one mile double circuit 115/69kV line between Tri-State’s La Junta Substation and Black Hills’s La Junta Substation.  This tie line will improve Black Hills’s load serving capability as well as provide backup service to Tri-State’s loads.  The in-service is 4Q 2012 at a Tri-State cost of $0.85 million.

5.	Lamar-Front Range Transmission Project – new project.

This project consists of a minimum of two major transmission components: a Lamar-Comanche 345kV line and a Lamar-Big Sandy-Missile Site 345kV line, with a potential extension to Vilas Substation.  The project would accommodate additional generation in Energy Resource Zones 2 and 3 in the context of Senate Bill 07-100. The project has also been identified by Tri-State as having the potential to accommodate future Tri-State resources in the same area.  Portions of the project could be constructed for 500kv operation and be integrated with the High Plains Express initiative.  The in-service date is 4Q 2017 at a cost to be determined.

6.	Henry Lake Substation Add and 230kV line, in-service date of 2nd Quarter 2010, no CPCN per Decision No. C09-0681.

7.	Bayfield 115/69kV Transformer Replace, in-service date of 2nd Quarter 2011, no   CPCN per Decision No. C09-0681.

8.	Bullock #2 115/69kV Transformer Replace, in-service date of 4th Quarter 2010, no CPCN per Decision No. C09-0681.

9.	Juanita T1 Transformer Replacement, in-service date of 4th 2010, no CPCN per Decision No. C09-0681.

10.	Lake Canal 230kV Sub, in-service date of 2nd Quarter 2012, no CPCN per Decision No. C09-0681.

11.	Lake Canal-Timnath-Carey 230kV Line, in-service date of 2nd Quarter 2012, no   CPCN per Decision No. C09-0681.

12.	LPEA-San Juan Project, in-service date of 4th Quarter 2015.  CPCN required per Decision No. C09-0681.

13.	Big Sandy-Lincoln-Midway 230kV Line, in-service date is 4th Quarter 2010, no CPCN required per Decision No. C08-0676.

14.	Hotchkiss 2-7.5 MVAR, 115kV Cap Addition, in-service 2nd Quarter 2010, no CPCN required per Decision No. C08-0676.

- 15.	Bayfield-Durango 115kV Line Uprate, in-service 4th Quarter 2010, no CPCN required per Decision No. C02-716.

- 16.	Beaver Creek-Erie 115kV to 230kV Double Circuit Upgrade Project, in-service date of 4th Quarter of 2010, CPCN granted per Decision No. C06-1384.

- 17.	Boomerang 115kV Delivery Point Project, in-service 2nd Quarter 2010, no CPCN required per Decision No. C06-0761.

- 18.	Deering Lake-Wray (T-S) 115kV Reliability Additions, in-service 4th Quarter 2010, no CPCN required per Decision No. C05-0826.

- 19.	North Park (Walden Tap) 230kV Emergency Project, in service date 4th Quarter 2010, no CPCN required per Decision No. C07-0553.

- 20.	Nucla-Telluride 115kV Transmission Line, in-service 4th Quarter 2012, CPCN granted per Decision No. C01-1059.

- 21.	Delta County 115kV Transmission Line Improvement (formerly Garnet Mesa 115kV Loop Service), in-service 4th Quarter 2011, no CPCN required per Decision No. C03-0707.

- 22.	East Montrose 115kV delivery Point, in-service 4th Quarter 2011, no CPCN required per Decision No. C06-0761.

- 23.	Erie 230/115kV Substation, in-service 4th Quarter 2010, no CPCN required per Decision No. C06-0761.

- 24.	FARR (formerly Granby) Pumping Plant-Windy Gap 138/69kV Double Circuit Loop Project (formerly Transmission Line Project), in-service 4th Quarter 2011, no CPCN required per Decision No. C90-1125.

- 25.	Richard Lake-Waverly 115kV Loop Project, in-service 4th Quarter 2010, no CPCN required per Decision No. C03-0707.

- 26.	Story 230kV Tie Line and 230kV Line Bay, in-service 4th Quarter 2010, no CPCN required per Decision No. C06-0761.

- 27.	United Power System Improvement Project – Phase II, in-service 4th Quarter 2011, no CPCN required per Decision No. C04-0725.

- 28.	Plaza-Waverly 115kV Loop Project, in service date 4th Quarter 2013, no CPCN required per Decision No. C07-0553.

- 29.	United Power System Improvement Project – Phase III, in-service 4th Quarter 2012, no CPCN required per Decision No. C04-0725.

- 30.	Panama 230kV Delivery Point Project, in-service date 2nd Quarter 2012, no CPCN required per Decision No. C07-0553.

- White River Electric Association, Inc.

#### Sulfur Creek Substation – new project.

This project builds a new 69-12.47kV Sulfur Creek Substation about one mile north of Meeker, Colorado adjacent to an existing 69kV line.  The substation is needed to serve existing and future loads in and around Meeker, Colorado.  The in-service date is January 2011 at a cost of $0.75 million.

## ORDER

### The Commission Orders That:

- Notice is hereby given that the above investor-owned utilities and rural electric cooperative associations have submitted information concerning the proposed construction of transmission and generation facilities in accordance with Rule 3206 of the Rules Regulating Electric Utilities, 4 Code of Colorado Regulations 723-3.  Pursuant to that rule, you are notified that the information is available for inspection at the offices of the Commission during regular business hours.

- Any interested person, firm, or corporation may file comments about the projects identified by the information now filed with the Commission within 15 days after the effective date of this Order.  The Commission will consider any comments in determining which projects do not require a certificate of public convenience and necessity, which projects will require the utility to file an application for a certificate of public convenience and necessity, or which projects will require the utility to file for a formal determination that a certificate is not required.

- This Order is effective upon its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
May 26, 2010.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO RONALD J. BINZ ________________________________ JAMES K. TARPEY ________________________________ - MATT BAKER ________________________________ - Commissioners |
| --- | --- |

/tmp/in/input.doc:SRS