# Decision No. C12-0194

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 08S-146G

RE: THE TARIFF SHEETS FILED BY PUBLIC SERVICE COMPANY OF COLORADO WITH ADVICE LETTER NO. 727-GAS.

ORDER GRANTING MOTION FOR EXTENSION OF TIME FOR FINAL REPORT AND WAIVER OF RESPONSE TIME

Mailed Date:  	February 24, 2012

Adopted Date:  	February 22, 2012

## BY THE COMMISSION

### Statement

- This matter comes before the Commission for consideration of a motion for an extension of time filed by Public Service Company of Colorado (Public Service or Company) on February 17, 2012.

- On October 24, 2008, the Hearing Commissioner, Chairman Ronald J. Binz, issued Recommended Decision No. R08-1l27. That decision concluded the Public Service Phase II gas rate case.  Public Service was directed to work together with a stakeholder group to finalize a new low income assistance program, covering design specifics, objectives, and evaluation criteria. Public Service was directed to prepare and file an interim status report after 18 months of program operations and a final report no later than 30 days after the end of the pilot period.

- On December 1, 2011, Public Service filed a Motion of Public Service Company of Colorado for an Extension of Time to File Final Report.  On the request of its consultant to the program, Public Service requested an extension of time to file its final report on the program, from a planned date of January 17, 2012 to February 17, 2012.  This delay was necessary to complete the analysis of the pilot program.  Public Service argues that no interested party should be harmed by this request for additional time and it will allow for a more thorough report.  No parties have filed opposition to the Motion.  By Decision No. C11-1380 issued December 23, 2011, that motion was granted.

- On Friday, February 17, 2012, Public Service filed a motion for an extension of time to file its final report regarding the natural gas low-income customer Pilot Energy Assistance Program and the Electric Assistance Program.  Public Service explains that the Company and its consultant are now finalizing the report.  Due to an unexpected death of an immediate family member of counsel, however, the Company requests an extension until Friday, February 24, 2012, to file the document.

- Now being duly advised in the matter, we find good cause has been stated and grant the motion and waive response time on our own motion.

## ORDER

### The Commission Orders That:

- The Motion of Public Service Company of Colorado for an Extension of Time to File Final Report filed on February 17, 2012 is granted.  The time to file the Pilot Energy Assistance Program final report originally due on February 17, 2012, is extended to February 24, 2012.

- Response time to the motion is waived.

- This Order is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
February 22, 2012.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JOSHUA B. EPEL ________________________________ JAMES K. TARPEY ________________________________ - MATT BAKER ________________________________ - Commissioners |
| --- | --- |