# Decision No. R12-0923

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 12A-351R

IN THE MATTER OF THE APPLICATION OF The regional transportation district for authoRIty to modify a grade-separated crossing by constructing commuter rail tracks under i-70 in the city and 
county of denver, state of colorado.

DOCKET NO. 12A-649R

IN THE MATTER OF THE APPLICATION OF bnsf railway company for authoRIty to modify a grade-separated crossing by removing 
freight rail tracks under i-70 in the city and county of denver, 
state of colorado.

RECOMMENDED DECISION OF 
ADMINISTRATIVE LAW JUDGE 
MANA L. JENNINGS-FADER 
PERMITTING LATE-FILED INTERVENTION 
AND GRANTING APPLICATIONS UNDER MODIFIED 
PROCEDURES AND SUBJECT TO CONDITIONS

Mailed Date:  August 8, 2012

TABLE OF CONTENTS

I.	STATEMENT	2

II.	FINDINGS, DISCUSSION, AND CONCLUSIONS	5

A.	Parties.	6

B.	The Grade-Separated Crossing.	6

C.	Amended RTD Application.	7

1.	Modifications to Crossing.	7

2.	Special Application Procedure.	10

D.	Amended BNSF Application.	11

III.	ORDER	14

A.	The Commission Orders That:	14

## STATEMENT

- On April 2, 2012, the Regional Transportation District (RTD) filed an Application with the Commission (RTD Application).  By that filing, RTD seeks authority to modify an existing grade-separated crossing by constructing new commuter rail tracks and by removing identified freight tracks under the existing Interstate 70 (I-70) structure located in Denver, Colorado.  By that filing, RTD also seeks Commission authorization to use the special application procedure described in the RTD Application.  That filing commenced Docket 
No. 12A-351R (RTD Docket).

- On April 11, 2012, the Commission gave public notice of the RTD Docket.  That Notice established an intervention period and a procedural schedule.  On July 20, 2012, Decision No. R12-0837-I vacated that procedural schedule.

- The following entities intervened in the RTD Docket:  the City and County of Denver (Denver) and the Union Pacific Railroad Company (UPRR).  Neither entity opposes or contests the RTD Application.

- On May 16, 2012, by Minute Order, the Commission deemed the RTD Application to be complete within the meaning of § 40-6-109.5, C.R.S.

- On June 7, 2012, BNSF Railway Company (BNSF) filed an Application with the Commission (BNSF Application).  By that filing, BNSF seeks authority to modify an existing

- grade-separated crossing by removing identified tracks and other facilities under the existing I-70 structure located in Denver, Colorado and seeks authority to add tracks east of those removed.  That filing commenced Docket No. 12A-649R (BNSF Docket).

- On June 12, 2012, the Commission gave public notice of the BNSF Docket.  That notice established an intervention period and a procedural schedule.  On July 20, 2012, Decision No. R12-0837-I vacated that procedural schedule.

- The following timely intervened in the BNSF Docket:  Denver and RTD.  Denver does not oppose or contest the BNSF Application.  RTD initially opposed the BNSF Application; RTD’s current position with respect to the BNSF Application is discussed below.

- On August 6, 2012, UPRR filed its Entry of Appearance and Notice of Intervention in the BNSF Docket.  UPRR made this filing after expiration of the intervention period.  For the following reasons, the ALJ will permit the late-filed intervention.  First, the BNSF Docket and the RTD Dockets are consolidated; as a result of its timely intervention in the RTD Docket, UPRR is a party in the consolidated proceeding.  Second, in its August 6, 2012 filing, UPRR states that it neither opposes nor contests the BNSF Application.  Granting UPRR permission to intervene in the BNSF Docket will not broaden the issues in this proceeding.

- On July 20, 2012, by Decision No. C12-0831-I, the Commission deemed the BNSF Application to be complete within the meaning of § 40-6-109.5, C.R.S.

- By Decision No. C12-0831-I, the Commission consolidated the RTD Application and the BNSF Application and referred the consolidated proceeding to an Administrative Law Judge (ALJ).

- RTD and BNSF, collectively, are the Applicants.  Denver and UPRR, collectively, are the Intervenors.  Applicants and Intervenors, collectively, are the Parties.

- On July 20, 2012, by Decision No. R12-0837-I and as pertinent here, the ALJ ordered Applicants to make, no later than August 3, 2012, a filing that met the requirements in that Order.  On August 3, 2012, RTD made the required filing, which contained a proposed procedural schedule including hearing dates.  For the reasons discussed below, the ALJ will not schedule an evidentiary hearing and will not establish a procedural schedule in this matter.  The August 3, 2012 filing is moot.

- On July 31, 2012, Applicants filed a Joint Motion to Amend Applications (Motion).  Appended to that filing were two documents:  Exhibit No. 1 (pertaining to the RTD Application) and Exhibit No. 2 (pertaining to the BNSF Application).

- Exhibit A to the RTD Application, as filed, contained the Civil Plan and Elevation for RTD’s proposed modification of the existing grade-separated crossing under the existing I-70 structure located in Denver, Colorado.  Exhibit A to the BNSF Application, as filed, contained the Civil Plan and Elevation for BNSF’s proposed track relocation at the same crossing.  In the Motion, Applicants sought permission to amend their applications as follows:  (a) substitute Exhibit No. 1 to the Motion for Exhibit A to the RTD Application; and (b) substitute Exhibit No. 2 to the Motion for Exhibit A to the BNSF Application.

- On August 6, 2012, by Decision No. R12-0903-I, the ALJ granted the Motion and permitted the requested amendment to the RTD Application and to the BNSF Application.  That Order amended the RTD Application and the BNSF Application.  As a result, the Civil Plans and Elevations in the two applications are consistent.

- In the Motion at ¶ 9, RTD stated that, if the Commission granted the Motion, RTD would file “a notice ... withdrawing its opposition to the [Amended] BNSF Application and allowing the [Amended] BNSF Application to proceed unopposed.”  On August 6, 2012, 
RTD filed a Notice That The Regional Transportation District Does Not Oppose 
(1) The BNSF Application (as Amended) and (2) This Matter Being Decided Without a Hearing.  By this filing, RTD withdraws its opposition to, and contest of, the Amended BNSF Application.

- The RTD Application, as amended, is neither opposed nor contested.

- The BNSF Application, as amended, is neither opposed nor contested.

- Pursuant to § 40-6-109(5), C.R.S., and Rule 4 Code of Colorado Regulations (CCR) 723-1-1403, an uncontested and unopposed application may be considered under the Commission’s modified procedure and without a formal hearing.  The ALJ finds that the uncontested and unopposed Applications in this consolidated docket can be, and should be, considered under the Commission’s modified procedure and without a formal hearing.

- In accordance with § 40-6-109, C.R.S., the ALJ now transmits to the Commission the record in this proceeding along with a written recommended decision.

## FINDINGS, DISCUSSION, AND CONCLUSIONS

- The Commission has subject matter jurisdiction in this consolidated proceeding pursuant to §§ 40-4-106(2)(a) and 40-4-106(3)(a), C.R.S.  For purposes of this consolidated proceeding, and pursuant to § 40-4-106(2), C.R.S., the Commission has personal jurisdiction over the Applicants.

- The Commission gave notice to all interested parties, including the adjacent property owners.

### Parties.

- Applicant RTD is a political subdivision of the State of Colorado.  RTD was established and is statutorily authorized to develop, to operate, and to maintain a mass transportation system for the District.  The District includes the Counties of Boulder, Denver, and Jefferson and portions of the Counties of Adams, Arapahoe, and Douglas.

- Applicant BNSF is a corporation in good standing in Colorado.  BNSF owns and operates track at the existing grade-separated crossing under the existing I-70 structure located in Denver, Colorado.

- Intervenor Denver is a legally created, established, organized, and existing home rule city, municipal corporation, and political subdivision under the provisions of article XX of the Colorado constitution and the Home Rule Charter of Denver.

- Intervenor UPRR is a corporation in good standing, in Colorado.  UPRR owns and operates track at the existing grade-separated crossing under the existing I-70 structure located in Denver, Colorado.

### The Grade-Separated Crossing.

- The BNSF crossing under I-70 is U.S. Department of Transportation National Crossing Inventory No. 245273X; and the milepost is 2.15.  Amended BNSF Application at ¶ 5.

- UPRR also has a crossing under I-70 at or near the location of the projects proposed in the Amended RTD Application and in the Amended BNSF Application.  Information pertaining to this UPRR crossing is not available on the Federal Railway Administration website, and UPRR did not provide this information in either of its interventions.

- At present, there are 16 daily train movements on the BNSF line at the crossing.  The maximum timetable speed is ten miles per hour (MPH).  No significant increase in the daily train movements on the BNSF line is anticipated.  At present, there are 14 daily train movements on the UPRR line at the crossing.  The maximum timetable speed is 45  MPH.

- The Average Daily Traffic (ADT) counts for motor vehicles at the crossing is 131,500 vehicles.  The speed limit for vehicles is 55 MPH.  As the crossing is grade-separated, neither Applicant provided information about projected ADT counts for motor vehicles.

- At present, there is no Northwest Electrified Segment commuter rail traffic at the crossing because there is no existing commuter rail track.  RTD estimates that, when the two proposed commuter rail lines are in service in 2016, there will be 184 commuter rail transit (CRT) movements per weekday through the crossing.  RTD does not anticipate a significant increase in the daily CRT movements.  The maximum CRT speed will not exceed 30 MPH.  Amended RTD Application at ¶ 7.

### Amended RTD Application.

#### Modifications to Crossing.

- The modifications that are the subject of the Amended RTD Application are proposed to be constructed in RTD’s FasTracks commuter rail transit line.  This line will operate between Denver Union Station in Denver, Colorado and the proposed Westminster Station in Westminster, Colorado.

- RTD requests authorization to construct, east of and adjacent to the BNSF tracks and under I-70 at the BNSF crossing, two commuter rail tracks with a catenary system that includes arc flash shield.  The modifications to be constructed include the addition of a soil nail retaining wall between the northbound tracks and the east bridge abutment and the addition of a protective barrier along the sides of the I-70 structure.  RTD also will remove the existing Denver Post Industry Track under I-70.  This is the RTD Project.

- Accompanying and incorporated into the Amended RTD Application are six exhibits.  Exhibit A consists of the civil plans and elevations for the proposed modifications.  Exhibit B is a vicinity map.  Exhibit C-1 shows track typical sections, Exhibit C-2 shows typical section and details of the protective barrier, and Exhibit C-3 shows typical section and details of the wall (soil nail) layout.  Exhibit D contains an itemized cost estimate for the RTD Project.

- Exhibit A, Exhibit C-1, Exhibit C-2, and Exhibit C-3 contain the crossing design plans for the RTD Project.  The new RTD commuter rail track locations will provide a minimum of 22.6’ of vertical clearance from the top of the RTD commuter rail to the bottom of the bridge structure.  There will be a minimum horizontal distance of 26.86’ between the existing BNSF freight track to the west and the closest proposed RTD commuter rail track.  The design allows for a 31.73’ distance between the closest proposed RTD commuter rail track and the new BNSF freight track east of the RTD commuter rail tracks.  There is a proposed 9’ minimum horizontal clearance between the RTD commuter rail track and the face of the wall to the west of the commuter rail track.  There will be a minimum horizontal clearance distance of 8’-6” from the centerline of the commuter rail track to the face of the overhead contact system pole.  There will be a 15’ clearance between the centerlines of the RTD commuter rail tracks.  The proposed clearances meet or exceed the minimum clearances required by Rule 4 CCR 723-7-7324, 
Rule 4 CCR 723-7-7325, and Rule 4 CCR 723-7-7326.

- The total estimated cost to construct the RTD Project is approximately $ 345,000.  RTD will pay all installation costs.  Amended RTD Application at ¶ 9.

- RTD plans to commence construction of the RTD Project upon approval of the Amended RTD Application and after BNSF has removed its freight tracks at the crossing.  RTD anticipates completion of construction within three years after construction commences.  RTD plans to have the two proposed commuter rail lines in service in January 2016.  Amended RTD Application at ¶ 10.

- The record supports granting the Amended RTD Application, subject to conditions.  Subject to the conditions stated in this Decision, the ALJ will grant the Amended RTD Application.

- Subject to the conditions enumerated in this Decision, the ALJ will authorize RTD to construct, and will order RTD to construct, the RTD Project as described in the Amended RTD Application and its appended exhibits.

- As a condition on granting the Amended RTD Application and authorizing the RTD Project, RTD will be ordered to inform the Commission in writing when the RTD Project is completed (RTD completion report).  RTD will be ordered to file the RTD completion report within ten calendar days of the date on which the RTD Project is completed.  The Commission expects the RTD completion report to be filed on or before July 31, 2015.  The Commission understands, however, that the RTD completion report may be filed earlier or later than July 31, 2015, depending on changes or delays to the planned construction schedule.

- As a condition on granting the Amended RTD Application and authorizing the RTD Project, RTD will be ordered to file, on or before July 31, 2015, a set of the final crossing design plans.

- As a condition on granting the Amended RTD Application and authorizing the RTD Project, and pursuant to Rule 4 CCR 723-7-7211(c), RTD will be ordered to maintain, at its own expense, the RTD Project that this Decision authorizes and directs RTD to construct.

#### Special Application Procedure.

- Construction of the RTD Project is on a design-build basis.  With a design-build process, design and construction may be performed concurrently; this means that the crossing design plans submitted with the Amended RTD Application (i.e., Exhibit A, Exhibit C-1, Exhibit C-2, and Exhibit C-3) may not be what is constructed.  In the usual case, RTD would file to amend the approved Amended RTD Application or its exhibits if the RTD Project as constructed was not consistent with the submitted crossing design plans.  RTD states that making such a filing can be expensive and time-consuming.

- Given the design-build nature of the Project, RTD proposes a special application procedure in order to avoid -- or, at least, to reduce -- the expense and time associated with filing to amend the approved Amended RTD Application or its exhibits in the event the RTD Project as constructed is not consistent with the submitted crossing design plans.  Amended RTD Application at ¶ 4.

- The proposal contains four elements.  First, the Commission allows the following Design-Build Parameters:  (a) the horizontal track location may move up to 3”; (b) the emergency walkway may move up to 3”; and (c) the approach grade of the commuter rail may change by up to 0.5 percent.  Second, if the final design of the RTD Project includes a change that exceeds the Design-Build Parameters, RTD must file an application to modify the 
Commission-approved RTD Project.  Third, if the final design of the RTD Project includes any reductions in clearance from any of the minimum clearances approved by the Commission, RTD must file a motion to permit the variance.  Fourth and finally,

- [n]o construction of any modification to an approved improvement that will cause such improvement to vary from submitted design in excess of the Design-Build Parameters, or [that will] cause such improvement to either exceed applicable Commission clearance requirements or [to] fail to comply with an existing variance may begin until [the Commission has ruled on] any amendments or petitions for variance that may be needed[.]

Amended RTD Application at ¶ 4.e.

- Subject to the condition stated below, the ALJ finds the proposed special application procedure to be reasonable, particularly in view of the fourth element (quoted above), as the procedure strikes a reasonable balance between the slight variances likely to result from the design-build process and the need for the Commission to review and to approve more significant changes to the RTD Project.  The ALJ will accept, subject to a condition. the special application procedure as described in the Amended RTD Application at ¶ 4.

- As a condition on granting the Amended RTD Application and authorizing RTD’s use of the special application procedure, RTD will be ordered to file, on or before July 31, 2015, a set of the final crossing design plans.

### Amended BNSF Application.

- BNSF requests authorization to modify its tracks at the existing grade-separated crossing at I-70 by removing the BNSF Jersey Cutoff freight tracks and constructing new tracks to the east of RTD’s CRT tracks that are part of the RTD Project.  This is the BNSF Project.

- Accompanying and incorporated into the Amended BNSF Application are three exhibits.  Exhibit A consists of the civil plan and elevation for the BNSF Project.  Exhibit B is a vicinity map.  Exhibit C contains an itemized cost estimate for the BNSF Project.

- Exhibit A contains the design plans for the BNSF Project.  The new BNSF freight track location will provide a minimum of 23.5’ of vertical clearance from the top of rail to the bottom of the bridge structure.  There will be a minimum horizontal distance of 26.86’ between the existing BNSF freight track to the west of the closest proposed RTD commuter rail track and a minimum of 31.73’ of horizontal distance between the closest proposed RTD commuter rail track and the new BNSF freight track to the east.  There is a proposed 17.28’ minimum horizontal clearance between the existing BNSF freight track and the wall located to the east of the existing BNSF track.  The proposed clearances meet or exceed the minimum clearances required by Rule 4 CCR 723-7-7324, Rule 4 CCR 723-7-7325, and Rule 4 CCR 723-7-7326.

- The total estimated cost of the BNSF Project is approximately $ 76,116.  RTD will pay all removal costs.  Amended BNSF Application at ¶ 8.

- BNSF plans to commence the BNSF Project upon Commission approval of the Amended BNSF Application.  BNSF anticipates completion of construction within three years after Commission approval.  Amended BNSF Application at ¶ 9.

- The record supports granting the Amended BNSF Application, subject to conditions.  Subject to the conditions stated in this Decision, the ALJ will grant the Amended BNSF Application.

- Subject to the conditions enumerated in this Decision, the ALJ will authorize BNSF to construct, and will order BNSF to construct, the BNSF Project as described in the Amended BNSF Application and its appended exhibits.

- As a condition on granting the Amended BNSF Application and authorizing the BNSF Project, BNSF will be ordered to inform the Commission in writing when the BNSF Project is completed (BNSF completion report).  BNSF will be ordered to file the BNSF completion report within ten calendar days of the date on which the BNSF Project is completed.  The Commission expects the BNSF completion report to be filed on or before July 31, 2015.  The Commission understands, however, that the BNSF completion report may be filed earlier or later than July 31, 2015, depending on changes or delays to the planned construction schedule.

- As a condition on granting the Amended BNSF Application and authorizing the BNSF Project, BNSF will be ordered to file, on or before July 31, 2015, a copy of the updated National Crossing Inventory Form reflecting the changes made to the crossing.

- As a condition on granting the Amended BNSF Application and authorizing the BNSF Project, BNSF will be ordered to maintain, at its own expense, the BNSF Project that this Decision authorizes and directs BNSF to construct.

- As a condition on granting the Amended BNSF Application and authorizing the BNSF Project, and pursuant to Rule 4 CCR 723-7-7211(a), BNSF will continue to be responsible for maintaining the tracks and appurtenances and the railroad equipment at the U.S. Department of Transportation National Crossing Inventory No. 245273X and milepost 2.15, State of Colorado.

- In accordance with § 40-6-109(2), C.R.S., the Administrative Law Judge recommends that the Commission enter the following order.

## ORDER

### The Commission Orders That:

- Consistent with the discussion above, the late-filed Entry of Appearance and Notice of Intervention in Docket No. 12A-649R filed by Union Pacific Railroad Company on August 6, 2012 is permitted.

- Union Pacific Railroad Company is an intervenor and a party in Docket 
No. 12A-649R.

- Subject to the conditions enumerated in this Decision, the Application filed by the Regional Transportation District (RTD) on April 2, 2012, as amended, is granted.

- Subject to the conditions enumerated in this Decision, RTD is authorized to construct, and shall construct, east of and adjacent to the BNSF tracks and under Interstate 70 
(I-70) at the BNSF Railway Company crossing, two commuter rail tracks with a catenary system that includes arc flash shield.  The modifications also shall include the addition of a soil nail retaining wall between the northbound tracks and the east bridge abutment and the addition of protective barrier along the sides of the I-70 structure and the removal of the Denver Post Industry Track, as described in the Application and its appended exhibits filed on April 2, 2012, as amended.  This is the RTD Project.

- The authority granted by Ordering Paragraph No. 4 is conditioned as follows:  RTD shall file a report with the Commission to inform the Commission when the RTD Project is completed (RTD completion report).  RTD shall file the RTD completion report within ten calendar days of the date on which the RTD Project is completed.  The Commission expects the RTD completion report to be filed on or before July 31, 2015.  That said, the Commission understands that the RTD completion report may be filed earlier or later than July 31, 2015, depending on changes or delays to the construction schedule.

- The authority granted by Ordering Paragraph No. 4 is conditioned as follows:  RTD shall file, on or before July 31, 2015, a set of the final crossing design plans for the RTD Project.

- The authority granted by Ordering Paragraph No. 4 is conditioned as follows:  RTD shall maintain, at its own expense, the RTD Project.

- RTD is authorized to use the Special Application Procedure described in paragraph 4 of the Application filed on April 2, 2012, as amended.  By this authorization, the Commission allows the use of the Design-Build Parameters described in ¶ 45, above.

- The authorization granted by Ordering Paragraph No. 8 is conditioned as follows:  the RTD shall file, on or before July 31, 2015, a set of the final crossing design plans for the RTD Project.

- Subject to the conditions enumerated in this Decision, the Application filed by BNSF Railway Company (BNSF) on June 7, 2012 is granted.

- Subject to the conditions enumerated in this Decision, BNSF is authorized to modify, and shall modify, its tracks at the existing grade-separated crossing at I-70 by removing the BNSF Jersey Cutoff freight tracks and constructing new tracks to the east of the RTD’s commuter rail transit tracks that are part of the RTD Project, as described in the Application and its appended exhibits filed on June 7, 2012, as amended.  This is the BNSF Project.

- The authority granted by Ordering Paragraph No. 11 is conditioned as follows:  BNSF Company shall file a report with the Commission to inform the Commission when the Project is completed (BNSF completion report).  BNSF shall file the BNSF completion report within ten calendar days of the date on which the BNSF Project is completed.  The Commission expects the BNSF completion report to be filed on or before July 31, 2015.  That said, the Commission understands that the BNSF completion report may be filed earlier or later than July 31, 2015, depending on changes or delays to the construction schedule.

- The authority granted by Ordering Paragraph No. 11 is conditioned as follows:  the BNSF shall file, on or before July 31, 2015, a copy of the updated National Crossing Inventory Form reflecting the changes made to the crossing.

- The authority granted by Ordering Paragraph No. 11 is conditioned as follows:  BNSF shall maintain, at its own expense, the BNSF Project.

- The authority granted by Ordering Paragraph No. 11 is conditioned as follows:  BNSF shall continue to be responsible for maintaining the tracks and appurtenances and the railroad equipment at U.S. Department of Transportation National Crossing Inventory No. 245273X and milepost 2.15, State of Colorado.

- The Commission retains jurisdiction to enter such orders as may be necessary to effectuate the purposes of this Decision.

- This Recommended Decision shall be effective on the day it becomes the Decision of the Commission, if that is the case, and is entered as of the date above.

- As provided by § 40-6-109, C.R.S., copies of this Recommended Decision shall be served upon the parties, who may file exceptions to it.

- If no exceptions are filed within 20 days after service or within any extended period of time authorized, or unless the recommended decision is stayed by the Commission upon its own motion, the recommended decision shall become the decision of the Commission and subject to the provisions of § 40-6-114, C.R.S.

- If a party seeks to amend, to modify, to annul, or to reverse a basic finding of fact in its exceptions, that party must request and pay for a transcript to be filed, or the parties may stipulate to portions of the transcript according to the procedure stated in § 40-6-113, C.R.S.  If no transcript or stipulation is filed, the Commission is bound by the facts set out by the administrative law judge; and the parties cannot challenge these facts.  This will limit what the Commission can review if exceptions are filed.

- If exceptions to this Recommended Decision are filed, they shall not exceed 30 pages in length, unless the Commission for good cause shown permits this limit to be exceeded.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO MANA L. JENNINGS-FADER ________________________________ Administrative Law Judge |
| --- | --- |

On August 6, 2012, UPRR filed an Amended Intervention.  This filing did not change UPRR’s position with respect to the RTD Application.

This Rule is found in the Rules of Practice and Procedure, Part 1 of 4 Code of Colorado Regulations 723.

This includes both the northbound CRT movements and the southbound CRT movements.

These Rules are found in the Rules Regulating Railroads, Rail Fixed Guideways, Transportation by Rail, and Rail Crossings, Part 7 of 4 Code of Colorado Regulations 723.

The Amended BNSF Application, which is discussed below, seeks authority to remove these tracks.

As set out above, this is also a condition on the Commission’s authorization to construct the RTD Project.