# Decision No. C13-1426

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING NO. 12A-1203R

IN THE MATTER OF THE APPLICATION OF THE CITY OF ARVADA FOR AUTHORITY TO EXTEND A DETACHED SIDEWALK ALONG THE NORTH SIDE OF THE 72ND AVENUE CROSSING OF THE UNION PACIFIC RAILROAD TRACKS, CITY OF ARVADA, JEFFERSON COUNTY, COLORADO.

commission decision granting 
request for fourth extension of time

Mailed Date:  November 15, 2013

Adopted Date:  November 13, 2013

## by the commission

### Statement

- This matter comes before the Public Utilities Commission (Commission or PUC) for consideration of a Request for PUC Order to Union Pacific to Produce Information to the City of Arvada on the Matter of the Construction and Maintenance Agreement (Request) filed by the City of Arvada (Arvada) on October 24, 2013, requesting the PUC require Union Pacific Railroad Company (UPRR) to provide an easement fee, easement agreement, and Construction and Maintenance Agreement to Arvada by November 8, 2013, and requesting an extension of time to December 31, 2013, to file the signed Construction and Maintenance Agreement.

- This matter also comes before the Commission for consideration of an Unopposed Request for Extension of Time to File the Finalized Construction and Maintenance Agreement (Motion) filed by Arvada on October 31, 2013 requesting an extension of time to December 31, 2013 to file the signed Construction and Maintenance Agreement.

- On January 14, 2013, Arvada filed a letter informing the Commission that it was Arvada’s understanding a Construction and Maintenance Agreement for the sidewalk additions was not necessary, and that no additional paperwork would be filed.

- On January 29, 2013, Arvada filed a Request for Extension of Time asking for an additional 90 days until April 30, 2013 to file the signed Construction and Maintenance Agreement.  The Commission granted this request by Decision No. C13-0215 mailed February 14, 2013.

- On April 30, 2013, Arvada filed its second Request requesting an additional 90 days of time up to and including July 29, 2013 to file the signed Construction and Maintenance Agreement in this matter.  The Commission granted this request by Decision No. C13-0607 mailed May 24, 2013.

- On July 29, 2013, Arvada filed its third Request requesting additional time up to and including October 28, 2013 to file the signed Construction and Maintenance Agreement in this matter.  The Commission granted this request by Decision No. C13-1041 mailed August 26, 2013.

- On October 24, 2013, Arvada filed the Request asking the Commission to require UPRR to provide the easement fee, easement agreement, and Construction and Maintenance Agreement to Arvada by November 8, 2013, and requesting an extension to December 31, 2013 to file the signed Construction and Maintenance Agreement.  Arvada filed this Request because it had provided the information to UPRR that UPRR had requested, but had yet to receive easement information from UPRR and had received no response from UPRR to the numerous requests for information from Arvada.

- On October 31, 2013, Arvada filed the Motion requesting an extension of time to December 31, 2013 and requesting withdrawal of its Request.

- As grounds for the Motion, Arvada states that it has conferred with counsel for UPRR on this matter.  Arvada and UPRR agree that additional time is needed to finalize the real estate matters now that the confusion regarding the requirements of a certain crossing have been clarified.  Arvada and UPRR expect to finalize the Construction and Maintenance Agreement as to form and content by November 15, 2013, and should be able to execute and file the signed Construction and Maintenance Agreement by December 31, 2013.

- No responses were filed to the Request or Motion.

- Now being fully advised in the matter, we grant the withdrawal of the Request and grant the Motion.

## ORDER

### The Commission Orders That:

- The City of Arvada’s Unopposed Request for Extension of Time to File the Finalized Construction and Maintenance Agreement filed on October 31, 2013 requesting an extension to December 31, 2013 to file the signed Construction and Maintenance Agreement is granted.

- The request of the City of Arvada to withdraw its Request for PUC Order to Union Pacific to Produce Information to the City of Arvada on the Matter of the Construction and Maintenance Agreement filed on October 24, 2013 is granted.

- The Commission retains jurisdiction to enter further decisions as necessary.

- This Decision is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
November 13, 2013.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JOSHUA B. EPEL ________________________________ JAMES K. TARPEY ________________________________ - PAMELA J. PATTON ________________________________ - Commissioners |
| --- | --- |