# Decision No. C18-0484

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING NO. 17A-0502R

IN THE MATTER OF THE APPLICATION OF CITY OF LOVELAND FOR AN ORDER AUTHORIZING THE ALTERATION OF THE AT-GRADE CROSSING OF THE BURLINGTON NORTHERN RAILWAY (BNSF) ADJACENT TO SOUTH RAILROAD AVENUE IN THE CITY OF LOVELAND.

commission decision GRANTING 
unopposed motion fOR EXTENSION OF TIME

Mailed Date:  	June 20, 2018

Adopted Date:  	June 20, 2018

## by the commission

### Statement

- This matter comes before the Commission for consideration of the City of Loveland’s Unopposed Motion for Extension of Time to File Construction and Maintenance Agreement with Burlington Northern Railway (Motion) filed by the City of Loveland (Loveland) on June 13, 2018, requesting until September 30, 2018 to file the signed agreement in this matter.

- As grounds, Loveland states that it executed a “Bridge Construction and Maintenance Agreement” with the BNSF Railway Company (BNSF) on April 13, 2018.  Loveland was not aware that a separate agreement was needed to address the crossing surface with BNSF that was the subject of the Application in this matter.  Loveland received a draft Construction and Maintenance Agreement for the crossing surface from BNSF on May 14, 2018.

- While Loveland believes this new Construction and Maintenance Agreement for the surface can be executed within the next 30 days, Loveland is currently awaiting a response from BNSF regarding Loveland’s comments to the agreement.  To provide adequate time, Loveland requests an extension of time to September 30, 2018 to file the signed Construction and Maintenance Agreement in this matter.  Loveland also states that no work has started at the crossing.

- Counsel for Loveland conferred with counsel for BNSF and can represent that the relief requested in this matter is unopposed.

- Now being fully advised in the matter, we grant the Motion.

## ORDER

### The Commission Orders That:

- The City of Loveland’s Unopposed Motion for Extension of Time to File Construction and Maintenance Agreement with Burlington Northern Railway filed by the City of Loveland (Loveland) on June 13, 2018, requesting until September 30, 2018 to file the signed agreement in this matter is granted.

- Loveland shall be required to file a copy of the signed Construction and Maintenance Agreement with the Commission by September 30, 2018 prior to the start of any construction work at the crossing.

- The Commission retains jurisdiction to enter further decisions in this matter as necessary.

- This Decision is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
June 20, 2018.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ FRANCES A. KONCILJA ________________________________ WENDY M. MOSER ________________________________ Commissioners |
| --- | --- |