# Decision No. C19-0454

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING NO. 17A-0698R

IN THE MATTER OF THE APPLICATION OF THE CITY OF THORNTON FOR AUTHORITY TO WIDEN 128TH AVENUE CROSSING FOR ROADWAY AND PEDESTRIAN IMPROVEMENTS; REMOVAL OF ACTIVE CROSSING WARNING DEVICES; INSTALLATION OF PASSIVE WARNING DEVICES AT REGIONAL TRANSPORTATION DISTRICT (US DOT 804303G) IN CITY OF THORNTON, ADAMS COUNTY, STATE OF COLORADO.

commission decision granting 
motion for extension of time

Mailed Date:  	June 3, 2019

Adopted Date: 	May 29, 2019

## by the commission

### Statement

- This matter comes before the Commission for consideration of a Motion for Extension of Time (Motion) filed by the City of Thornton (Thornton) on May 8, 2019 requesting an extension of time to July 1, 2020 to complete the widening of the 128th Avenue crossing.

- As grounds, Thornton states that the extension of time is needed because of the necessity to replace a water line beneath 128th Avenue before the widening improvements can begin.  The waterline project will be completed in late May 2019 and the crossing widening can then begin in late June 2019 once the construction bid opening has occurred on May 31, 2019.  Thornton states it would be in the best interests of the traveling public and taxpayers to widen and improve 128th Avenue after the water line improvements are completed.

- No comments were filed to the Motion.

- Now being fully advised in the matter, we grant the Motion.

## ORDER

### The Commission Orders That:

- The Motion for Extension of Time filed by the City of Thornton (Thornton) on May 8, 2019 requesting an extension of time to July 1, 2020 to complete the widening of the 128th Avenue crossing is granted.

- Thornton is granted an extension of time to July 1, 2020 to complete the widening of the 128th Avenue project and to file the project completion letter and updated National Inventory Form for the project.

- The Commission retains jurisdiction to enter further decisions as necessary.

- This Decision is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
May 29, 2019.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ FRANCES A. KONCILJA ________________________________ JOHN GAVAN ________________________________ Commissioners |
| --- | --- |