# Decision No. C20-0369

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING NO. 20A-0070R

IN THE MATTER OF THE APPLICATION OF THE E-470 AUTHORITY FOR AUTHORITY TO WIDEN TWO EXISTING HIGHWAY OVERPASS BRIDGES CROSSING OVER TRACKS OWNED BY UNION PACIFIC RAILROAD COMPANY, USDOT NO. 906-536L, IN ADAMS COUNTY, STATE OF COLORADO.

commission decision granting 
request to modify filing deadlines

Mailed Date:  	May 18, 2020

Adopted Date: 	May 13, 2020

## by the commission

### Statement

- This matter comes before the Commission for consideration of a Request to Modify Filing Deadlines (Motion) filed by the E-470 Authority (E-470) on April 28, 2020, requesting to modify filing deadlines ordered by Decision No. C20-0233, mailed April 13, 2020, due to issues caused by the current novel coronavirus pandemic (COVID-19).

- The original Application filed by E-470 on February 26, 2020, stated construction would start by May 1, 2020 and be completed by December 31, 2020.

- E-470 is now requesting to change the dates so that the signed Construction and Maintenance Agreement is filed with the Commission around November 1, 2020.

- As grounds for this request, E-470 states that it has had recent discussions with the Union Pacific Railroad (UPRR) representatives regarding the Construction and Maintenance Agreement.  UPRR has informed E-470 that the Construction and Maintenance Agreement may require six to nine months to complete due, in part, to recently announced furloughs for UPRR staff as a result of the pandemic.  UPRR is optimistic the process could be completed more quickly, however, they have recommended that E-470 anticipate the signed Construction and Maintenance Agreement by November 1, 2020.

- There were no responses to the Motion.

- The original Application was filed prior to the start of the effects of COVID-19, over which Colorado Governor Jared Polis declared a state of emergency.  In addition to the stated furloughs at UPRR necessitated by COVID-19, we recognize that effective management of the challenges presented by COVID-19, given the timing of the original Application, additionally supports the requested extension of time to file the signed Construction and Maintenance Agreement by November 1, 2020.

- We find that good cause exists to grant the Motion consistent with the above discussion.

## ORDER

### The Commission Orders That:

- The Request to Modify Filing Deadlines filed by the E-470 Authority (E-470) on April 28, 2020, requesting to modify filing deadlines ordered by Decision No. C20-0233, mailed April 13, 2020, due to issues caused by the current novel coronavirus pandemic (COVID-19) is granted.

- E-470 shall provide the signed Construction and Maintenance Agreement by November 1, 2020.

- The Application as amended is granted.

- E-470 is authorized and ordered to proceed with the widening of E-470 Highway bridge structures over the tracks of the Union Pacific Railroad Company near Aurora, Colorado.

- The remaining requirements from Decision No. C20-0233 remain in effect with the understanding that the project completion will occur after the original December 31, 2020 date contained within that Decision.

- The Commission retains jurisdiction to enter further decisions as necessary.

- This Decision is effective on its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
May 13, 2020.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ JOHN GAVAN ________________________________ MEGAN M. GILMAN ________________________________ Commissioners |
| --- | --- |

In this instance, given the timing of the filing of the initial Application and Governor Polis’ declaration of a state of emergency, we recognize this declaration on our own motion.  Any future filings should continue to specify whether COVID-19 considerations, or any other pertinent circumstances, support the requested action.