# Decision No. C19-0509-I

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

PROCEEDING NO. 16A-0396E

IN THE MATTER OF THE APPLICATION OF PUBLIC SERVICE COMPANY OF COLORADO FOR APPROVAL OF ITS 2016 ELECTRIC RESOURCE PLAN.

INTERIM decision requiring additional information regarding motion
 for extension of 18-month competitive acquisition deadline under RULE 3613(I)

Mailed Date:  	June 14, 2019

Adopted Date: 	June 12, 2019

## by the commission

### Statement

- On May 24, 2019, Public Service Company of Colorado (Public Service or Company) filed a Motion Pursuant to Rule 3613(i) for Extension of the 18 Month Deadline to Execute Contracts (Motion). This Motion seeks an extension to execute contracts for the resources approved by Decision No. C18-0761 (Phase II Decision). In the Motion, Public Service states that it cannot execute contracts for two bids approved in the Phase II Decision under the terms of the bids and provides a general outline of its proposal to solicit targeted bids and then file an amendment to request Commission approval for its proposed alternatives. The Company also requests a corresponding extension of time to release confidential and highly confidential information pursuant to Rule 3613(j)-(k) of the Commission’s Rules Regulating Electric Utilities, 4 Code of Colorado Regulations 723-3.

- As discussed below, we require Public Service to provide additional information regarding its proposed plan to solicit targeted bids and file an Electric Resource Plan (ERP) amendment.

### Background, Summary of Motion

- On September 10, 2018, the Commission issued Decision No. C18-0761 approving the Colorado Energy Plan (CEP) portfolio in the Company’s 120-Day Report.  Consistent with ERP Rules, Public Service states that it has pursued this cost-effective resource plan with further due diligence and contract negotiations.

- Rule 3613(i) requires Public Service to complete the competitive acquisition process by executing contracts within 18 months after the utility’s receipt of bids. Rule 3613(i) further provides that the utility may file a motion in the resource plan proceeding requesting to extend this deadline for good cause shown.

- On May 24, 2019, Public Service filed the Motion pursuant to Rule 3613(i).  The Company states that it conferred with all parties, and listed party responses as: did not respond, no objection, no position, or no position but reserves the right to respond.  See Motion p. 2.  Responses to the Motion were due June 7, 2019, but no party responded to the Motion.

- In the Motion, Public Service states that one developer who had two bids in the CEP portfolio that was approved in the Phase II Decision cannot complete the bids as proposed, and Public Service is requesting additional time to conduct an additional targeted resource solicitation.  One of the bids was for a 110 MW solar facility with 50 MW storage, and the other was for a 75 MW solar facility.  These bids were to provide 185 MW of nameplate capacity and 109 MW of load carrying capacity.

- The Company states that it needs more time to conduct a targeted solicitation for the replacement projects and states that it will file for an ERP amendment after bids are received. The Company proposes to seek similar size, technology, and pricing to meet the same December 31, 2022 commercial operations date of the two failed projects. The bid evaluation will be conducted consistent with the methodologies and assumptions approved in the Phase I Decision.

- Public Service states that it will then file an amendment for Commission approval, including: a summary of bids received; a levelized cost of energy and net present value analysis of bids; and the results of Strategist modeling of the costs and benefits of potential replacement projects relative to the originally-approved CEP. The Company states that it intends to offer alternatives to the Commission, ranging from no action to full replacement depending on the cost-effectiveness of bids received, along with a preferred alternative based on relevant analyses. The Company will strive to file the ERP Amendment by mid-September 2019.

- Public Service includes that it plans to provide advanced notification to potential bidders of the pending Request for Proposals (RFP) in early June 2019 and issue the RFP by July 1, 2019 with bids due by August 1, 2019. The bid evaluation process is targeted to occur between August 1, 2019 and early September 2019.

- Public Service is also requesting a corresponding extension of time to comply with the requirements of Rules 3613(j)-(k) as set forth in Decision No. C19-0249, which requires Public Service to publicly release confidential and highly confidential information related to bids upon completion of the competitive acquisition process pursuant to Rule 3613(i).

### Discussion

- We find that the limited discussion about the procedures for conducting a targeted solicitation, as presented in Public Service’s Motion, raises a number of questions about the details of the Company’s plan for re-bidding.  Public Service indicates that it does not intend to file for Commission approval of its targeted solicitation prior to issuing the RFP. The ERP process is centered on the Commission approving an acquisition plan, and then the utility solicits bids consistent with that plan.  However, in this case Public Service proposes only to solicit Commission approval after bids are received, and provides only summary-level information about its proposed plan.

- Therefore, we require Public Service to present a detailed project plan, which explains in detail all aspects of its proposed targeted solicitation, including:

- a)	Full details of what type and amount of resources it is seeking;

- b)	Whether these resources will be procured at any cost, or whether the costs must be within the level of the bids approved in the Phase II Decision;

- c)	Whether resources must be bid in a similar location as the previous bids, or how differing bid locations will be addressed;

- d)	An analysis of whether these resources could be procured as a part of the Company’s next ERP solicitation under the “zero need” assessment in the previous solicitation if bid costs exceed the levels of the approved CEP portfolio;

- e)	Why the Company cannot use back-up bids from the Phase II solicitation to replace the failed bids;

- f)	Whether all confidential and highly confidential information will be held from public release, or whether only the new bid information will be held; and

- g)	A proposed timeline, including how long of an extension is requested for the 18-month deadline to execute contracts and confidential information extension.

- We require Public Service to file this information on or before July 1, 2019, to coincide with its proposed RFP issuance date.

- Regarding Public Service’s proposed extension for the release of confidential and highly confidential information, as included above, the Commission requires more information on the extension requested by Public Service to comply with the requirements of Rules 3613(j)-(k). We find it appropriate to retain all such information as confidential or highly confidential, as designated, until further order of the Commission, such that we can consider the additional information Public Service provides before ruling on the merits of the requested extension.

## ORDER

### It Is Ordered That:

- On or before July 1, 2019, Public Service Company of Colorado shall file additional information as discussed above.

- This Decision is effective upon its Mailed Date.

### ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
June 12, 2019.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | - THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO JEFFREY P. ACKERMANN ________________________________ FRANCES A. KONCILJA ________________________________ JOHN GAVAN ________________________________ Commissioners |
| --- | --- |

Decision No. C19-0249 was issued in this proceeding on March 20, 2019.