# Decision No. C99-27

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

DOCKET NO. 98V-567T

IN THE MATTER OF RYE telephone company’s REQUEST FOR temporary VARIANCE FROM THE REQUIREMENTS OF Section 251(b)(3) of the telecommunications act of 1996.

ORDER granting in part a temporary VARIANCE

Mailed Date:  January 8, 1999

Adopted Date:  January 6, 1999

## I.	BY THE COMMISSION

### Statement and Findings of Fact

- On December 7, 1998, Rye Telephone Company (“Rye”), filed an Application requesting a temporary waiver of the federal requirement to offer interLATA dialing parity, or “1+” equal access in its Kim exchange.  In effect, Rye requests a Commission determination that it need not implement equal access on February 8, 1999, as ordered by the Federal Communications Commission (“FCC”) in FCC 96-333, but can extend time for imple-mentation for the Kim exchange until February 8, 2000.

- In it application, Rye states that it will soon upgrade a switch that is not capable of providing dialing parity, a Redcom (version 12), to a switch that is capable of providing dialing parity. Rye further states that this upgrade will be com-pleted during the second quarter of 1999.

- Rye is seeking to be relieved of the February 8, 1999 implementation date because it anticipates upgrading its switch equipment during the second quarter of 1999 and initiating the mandatory, six-month balloting process for equal access shortly afterwards.

- Pursuant to § 251(f)(2) of the Telecommunications Act of 1996, local exchange carriers with less than 2 percent of the nation’s access lines are given the opportunity to petition state commissions for a suspension or modification of the § 251(b)(3) requirements.  Section 251(f)(2) states:

- The State commission shall grant such petition to the extent that, and for such duration as, the State commission determines that such suspension or modifica-tion –

- (A)	is necessary-

- (i)	to avoid a significant adverse eco-nomic impact on end users of telecom-munications services generally;

- (ii)	to avoid imposing a requirement that is unduly economically burdensome; or

- (iii)	to avoid imposing a requirement that is technically infeasible; and

- (B)	is consistent with the public interest, con-venience, and necessity.

- Rye also states in its application that no Inter-exchange Carriers have submitted a request to Rye for equal access in the Kim exchange.

- As noted above, § 251(f)(2) of the Telecom-munications Act of 1996, states that this Commission may permit a waiver or variance from the rules if compliance is unduly economically burdensome.  This Commission will grant, in part, a temporary variance of the requirements of FCC 96-333.  Spe-cifically, we will grant a waiver of the February 8, 1999 implementation date for equal access.  Rye will not be required to begin 1+ equal access or dialing parity until August 8, 1999, six months after the February 8, 1999 federal requirement.  We find no good cause shown why Rye cannot begin the required balloting process for equal access implementation concurrent with its switch upgrade.  This partial grant should be enough time for Rye to complete both its switch upgrade by the end of the second quarter of 1999, and allow an additional two months for any problems with the new switch to be solved and for completion of the equal access implementation process.

- If Rye’s switch upgrade is not completed by the end of June 1999, it may request an additional period of time before implementing equal access in its Kim exchange.  This request for additional time may be made in a letter filed in this docket signed by Rye’s General Manager.

## II.	ORDER

### A.	The Commission Orders That:

- This Application of Rye Telephone Company is hereby deemed complete.

- Rye Telephone Company is hereby granted a tem-porary variance from the requirements of Federal Communications Commission Order 96-333 until August 8, 1999 consistent with the above discussion.

- This Order is effective on its Mailed Date.

### B.	ADOPTED IN COMMISSIONERS’ WEEKLY MEETING
January 6, 1999.

THE PUBLIC UTILITIES COMMISSION
OF THE STATE OF COLORADO



ROBERT J. HIX
________________________________



VINCENT MAJKOWSKI
________________________________



R. BRENT ALDERFER
________________________________
Commissioners

Commissioners

( S E A L )

ATTEST:  A TRUE COPY

____________________

Bruce N. Smith

Director

g:\yellow\98V567T