# Decision No. C06-0761

BEFORE THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO

CASE NO. 6396

IN THE MATTER OF THE DESIGNATION OF ELECTRIC UTILITY TRANSMISSION FACILITIES AND ELECTRIC UTILITY GENERATION FACILITIES FOR WHICH AN APPLICATION TO OBTAIN A CERTIFICATE OF PUBLIC CONVENIENCE AND NECESSITY IS REQUIRED OR THE FILING OF A FORMAL DETERMINATION THAT NO CERTIFICATE IS REQUIRED.

Order REGARDING
certification of facilities

Mailed Date:  July 3, 2006

Adopted Date:  June 28, 2006

## BY THE COMMISSION

### Statement

- Rule 3205(c) and Rule 3206(c) of the Commission’s Electric Utility Rules, 4 Code of Colorado Regulations 723-3, require each Colorado electric utility to file a schedule of its proposed new construction or extensions of generation and transmission facilities for the next three calendar years, no later than April 30 of each year.

- Rule 3205(f)(l) and Rule 3206(h)(l) further provide that the Commission shall issue its decision on whether a certificate of public convenience and necessity (CPCN), or a formal determination regarding the necessity of a CPCN, is required within 60 days of April 30 of the calendar year in which the data are filed.

- Rules 3205(d) and 3206(f) provide that the Commission will give notice of the filing of data to all those who, in the opinion of the Commission, are interested persons, firms, or corporations.  Any interested person, firm, or corporation may file comments concerning the identified projects within 15 days of the filing of the data.

- The Commission issued notice of the data filing on May 26, 2006, and a 15-day period for comments ended June 12, 2006.  Mr. Craig Cox, Executive Director, Interwest Energy Alliance, provided comments on June 16, 2006.  His request/comments were beyond the scope and intent of these filings.

- The following utilities submitted proposed projects:

- Mountain View Electric Association, Inc.

- Public Service Company of Colorado

- Intermountain Rural Electric Association, Inc.

- Tri-State Generation and Transmission Association, Inc.

- White River Electric Association, Inc.

- Aquila, Inc.

- Highline Electric Association, Inc. – late submittal

- New projects were reported as listed below by company:

- Mountain View Electric Association, Inc.

- Anderson Substation in-service August 2007

- Lorson Ranch Substation  in-service August 2006

- Rolling Hill Substation in-service August 2007

- Santa Fe Spring Substation and 115kV Transmission Line in-service 
August 2007

- Schriever Air Force Base Substation #2 and 115kV Transmission Line
in-service 2008

- Public Service Company of Colorado

- Front Range 230-13.8kV Substation in-service May 2007

- Isabelle 230-13.8kV Substation in-service May 2007

- Highly Confidential Data Sets 1, 2, 3, and 4

- Powhaton 230-13.8kV Substation in-service May 2008

- Intermountain Rural Electric Association, Inc.

- Daniels Park Substation 115-12.47kV Transformer in-service May  2007

- Crowfoot Valley Substation in-service July 2007

- Delbert Substation in-service July 2008

- Hartsel Substation in-service September 2008

- Hartsel-Fairplay 115kV Transmission Line in-service October 2008

- Fairplay Substation in-service October 2008

- Shawnee Substation in-service October 2008

- Como Substation in-service September 2009

- Fairplay-Como 115kV Transmission Line in-service September 2009

- Happy Canyon Substation in-service June 2009

- Victory Substation in-service September 2009

- Victory 115kV Transmission Tap in-service September 2009

- Dawson Ridge Substation in-service December 2009

- Wolfensberger-Dawson Ridge 115kV Transmission Line in-service December 2009

- Pine Junction Substation in-service September 2009

- Tri-State Generation and Transmission Association, Inc.

- East Montrose 115kV Delivery Point in-service 1stQ 2008

- Erie 230/115kV Substation in-service 1stQ 2010

- Story 230kV Tie Line and 230kV Line Bay in-service 1stQ 2010

- Boomerang 115kV Delivery Point Project in-service 4thQ 2007

- Comanche-Stem Beach-Walsenburg 115kV Line 1stQ 2009

- White River Electric Association, Inc.

- Wolf Ridge Substation and 138kV Line in-service December 2006

- Wolf Ridge-Yankee Gulch 138kV Transmission Line in-service September 2006

- Aquila, Inc.

- Freemary Substation in-service June 2008

- Reader-Airport 115kV transmission Line in-service September 2009

- High Line Electric Association, Inc.

- Plainview Substation 115X69-12.47kV and 2 miles of 115/69kV
Transmission Line in-service July 2007

- Interstate Substation – add 115-69kV Transformer in-service July 2007

## ORDER

### The Commission Orders That:

- No certificate of public convenience and necessity (CPCN) shall be required for the following White River Electric Association, Inc. projects:

- Wolf Ridge Substation and 138KV Line

- Wolf Ridge-Yankee Gulch 138kV Transmission Line

- No CPCN shall be required for the following Public Service Company of Colorado projects:

- Front Range 230-13.8kV Substation

- Isabelle 230-13.8kV Substation

- Highly Confidential Data Sets 1 and 2

- Powhaton 230-13.8kV Substation

- No CPCN shall be required for the following Intermountain Rural Electric Association, Inc. projects:

- Daniels Park Substation 115-12.47kV Transformer

- Crowfoot Valley Substation

- Delbert Substation

- Hartsel Substation

- Hartsel-Fairplay 115kV Transmission Line

- Fairplay Substation

- Shawnee Substation

- Como Substation

- Fairplay-Como 115kV Transmission Line

- Happy Canyon Substation

- Victory Substation

- Victory 115kV Transmission Tap

- Dawson Ridge Substation

- Wolfensberger-Dawson Ridge 115kV Transmission Line

- Pine Junction Substation

- No CPCN shall be required for the following Highline Electric Association, Inc. projects:

- Plainview Substation 115X69-12.47kV and 2 miles of 115/69kV
Transmission Line in-service July 2007

- Interstate Substation – add 115-69kV Transformer in-service
July 2007

- Public Service Company of Colorado shall file for a CPCN or for a formal determination that no CPCN is required for the following projects:  a) Comanche-Midway-Daniels Park 345kV Line, in-service May 2009 – an application for a CPCN determination was filed February 16, 2005, under Docket No. 05A-072E – decision is pending; b) Sandown-Leetsdale 115kV Line, in-service May 2009–CPCN filed May 2, 2006 under Docket No. 06A-259E; and c) Highly Confidential Data Sets 3 and 4.  The filing shall include, but shall not be limited to:

- (a)	a map showing the general area or actual locations where facilities will be constructed, population centers, major highways, state boundaries, county boundaries;

- (b)	electric one line diagrams including substation one line diagrams;

- (c)	information on alternatives studied, costs for those alternatives, criteria used to rank or eliminate alternatives;

- (d)	justification for the preferred alternative, including technical and/or economic studies;

- (e)	demonstration that the public convenience and necessity of Colorado consumers require granting of the application; and

- (f)	a report of prudent avoidance measures considered and justification for the measures selected to be implemented.

- Tri-State Generation and Transmission Association, Inc. shall file for a CPCN or for a formal determination that no CPCN is required for the following projects:  a) Durango-Hesperus 115kV Loop Project, in-service 1stQ 2008, per Decision No. C03-0707; b) Archuleta County System Improvement Project (formerly Bayfield-Pagoda 115kV Loop Project), in-service 1stQ 2011, per Decision No. C03-0707; c) San Luis Valley 230kV Loop (formerly San Luis Valley-Walsenburg 230kV Line), in-service 1stQ 2010, CPCN determination required per Decision No. C03-0707; and d) Comanche-Stem Beach-Walsenburg 115kV Line, in-service 1stQ 2009.  The filing shall include, but shall not be limited to:

- (a)	a map showing the general area or actual locations where facilities will be constructed, population centers, major highways, state boundaries, county boundaries;

- (b)	electric one line diagrams including substation one line diagrams;

- (c)	information on alternatives studied, costs for those alternatives, criteria used to rank or eliminate alternatives;

- (d)	justification for the preferred alternative, including technical and/or economic studies;

- (e)	demonstration that the public convenience and necessity of Colorado consumers require granting of the application; and

- (f)	a report of prudent avoidance measures considered and justification for the measures selected to be implemented.

- No CPCN shall be required for the following Tri-State Generation and Transmission Association, Inc. projects:

- East Montrose 115kV Delivery Point

- Erie 230/115kV Substation

- Story 230kV Tie Line and 230kV Line Bay

- Boomerang 115kV Delivery Point Project

- This Order is effective on its Mailed Date.

### ADOPTED IN Commissioners’ WEEKLY MEETING
June 28, 2006.

| (S E A L) ATTEST: A TRUE COPY Doug Dean, Director | THE PUBLIC UTILITIES COMMISSION OF THE STATE OF COLORADO GREGORY E. SOPKIN ________________________________ POLLY PAGE ________________________________ CARL MILLER ________________________________ Commissioners |
| --- | --- |

/tmp/in/input.doc:SRS